## Products
Manufacturer | Model # | Description | Image URL | Finish/Color

## Vendor
Vendor
Ferguson
Ferguson Home
Home Depot
Menards
Lowes
Standard Lumber
Amazon
ProSource Wholesale
Lucky Jackass
CACJR Granite
Standard Lumber

## Manufacturer
Manufacturer
Kohler
Moen
Delta
Signature
American Standard
Daltile
WW Woods

## APIA ITEMS
ITEM
Faucet
Shower Trim
Shower Arm
Shower Head
Shower Arm Diverter Valve
Shower Handheld
Shower Elbow
Shower Vacuum Breaker
Shower Handheld Slide Bar
Shower Slide Bar Trim Kit
Toilet
Toilet Seat
Toilet Tank Lever

## Frequent Material Model Price
URL for PPT
This is a list of material that the guys say are not Mega Standard | Material Frequent Used -
Date | Item Description |  | Vandor | Cost from Them Plus 15% | Model
2025-10-24 | Panasonic 100 CFM 0.9 Sone Ceiling Mounted HVI Certified Exhaust Fan | https://www.fergusonhome.com/panasonic-fv-0510vs1/s1286588?uid=3162516 | Service Plus | 92 | Model # BLMC2432
2025-10-24 | Panasonic 100 CFM 0.5 Sone Ceiling Mounted LED Lighted Exhaust Fan with Smart Flow Technology | https://www.fergusonhome.com/panasonic-fv-0510vsl1/s1367152?uid=3217466 | Service Plus | 155.25 | Model: FV-0510VSL1

## Material DON'T USE
This is a list of material that the guys say are not Mega Standard
Date | Item Description | Vandor | Job | Model | Why
2025-10-24 | Elega 24 in. W x 32 in. H Rectangular Aluminum Recessed/Wall Mount Dimmable Fogless Lighted Medicine Cabinet with Mirror | Home Depot | Garwood | Model # BLMC2432
2025-10-24 | Kohler Tub Spouts - | Ferguson | Marr, Brummond | all models | No Slip Flipat install, tighting against the wall. Told Jason at Ferguson and Kohler doesn't make any other kind.

## Add on Formula
Add-On Formula for Subs
Example
Material Costs | 102.83 | 151.2206
Sub - Addon | 2400 | 3529.4118

## Vance, Stacey & Terry 39505-LNC
Bath Remodel
| Terry & Stacey Vance | Model | Allowance | Actual Cost | Vendor | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
Powder Room | [6 empty] | FALSE |  | FALSE
| Vanity 21 x 30 Hanover / Carbon |  | 3200 | 3100 | Shiloh Order | 2025-11-21 | TRUE |  | FALSE
| Hardware Handles | K-26640-2MB |  | 61.138 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Quartz Top Back & Side Splash SQUARE | Calacatta Botanica |  |  | CACJR Granite Quote REQ 11/22 |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
| Sink | K-2209-0 | 300 | 99.198 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Faucet & Drain | K-22022-4-2MB | 350 | 357.962 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Toilet | K-30810-0 | 300 | 416.9 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Toilet Paper Holder | K-21954-2MB |  | 68.013 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Towel Ring | K-21955-2MB |  | 50.996 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Mirror | K-26050-BLG | 400 | 227.931 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Vanity Light | K-31757-S03-2GL | 350 | 364.518 | Ferguson | 2025-11-21 | TRUE |  | FALSE
[7 empty] | FALSE |  | FALSE
Paint | Paint 2 Colors Twilight 2058-10 & Garytint 1611 |  |  |  | Benjamin Moore | 2025-11-22 | TRUE |  | FALSE
| Ceiling White | [5 empty] | FALSE |  | FALSE
| Trim | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Doors & BaseBoard | [6 empty] | FALSE |  | FALSE
| 4 Doors - 2 Panel Solid |  | 2100 |  |  |  | FALSE |  | FALSE
| 3- Door Knobs 2 passage 1 privacy | [5 empty] | FALSE |  | FALSE
| 1 Bi-Fold Knobs Matte Black |  |  | 12.35 | Wayfair | 2025-11-22 | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
| Total Allowances to Actual Costs |  | 7000 | 4759.006 |  |  | FALSE |  | FALSE
| Allowance | [5 empty] | FALSE |  | FALSE
| Over Allowance Materials Add-On |  |  | 4759.006 |  |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
| Total Allowances |  | 14000

## Roloff 39337-THC Bath
Basement Remodeling Selection, Ordering & Receiving Checklist
Christine Roloff 39337-THC Master Bath |  |  | Model # | Allowances | Actual Cost | Vendor | Ordered Date |  | Received & Inspected Date
1. Selection Phase (Choosing materials and finishes)
| FALSE | *** Permit Allowance - |  | 250 |  |  |  | FALSE
Electrical - Reccessed all | FALSE | LED recessed lights |  | 1700 |  | Service Plus |  | FALSE
Electrical - Bath | FALSE | (2) Bath Exhusted Fan |  |  |  | Service Plus |  | FALSE
Electrical - Bath | FALSE | (3) Wall Sconces | S 2165BZ-CG |  | 1792.56 | Ferguson |  | FALSE
Electrical - Bath | FALSE | Recessed Shower Light |  |  |  | Service Plus |  | FALSE
| FALSE | (2) Lighted 24 x 30 Medicine Cabinet over the sinks | K-99007-TLC-NA |  | 2349.38 | Ferguson |  | FALSE
| FALSE | [6 empty] | FALSE
| FALSE | [6 empty] | FALSE
Bathroom Plumbing |  | Allowance for Bath |  | 2000 |  |  |  | FALSE
| FALSE | Shower Double Handle Trim | UT36111ORB |  | 388.806 | Ferguson |  | FALSE
Bathroom Plumbing | FALSE | Shower Valve | U232CIS |  | 198.935 | Ferguson |  | FALSE
| FALSE | Shower Head | 3638ORB |  | 173.525 | Ferguson |  | FALSE
| FALSE | Shower Arm | 10154ORB |  | 36.597 | Ferguson |  | FALSE
| FALSE | Shower Arm Flange | M164745ORB |  | 19.459 | Ferguson |  | FALSE
| FALSE | Shower Handheld w/Slide Bar | M3667EPORB |  | 535.502 | Ferguson |  | FALSE
| FALSE | Shower Wall Elbow Supply | A725ORB |  | 72.072 | Ferguson |  | FALSE
| FALSE | Shower Vacuum Breaker | MA714ORB |  | 161.546 | Ferguson |  | FALSE
| FALSE | Schulter Shower Drain Kit Oil Rubbed Bronze |  |  |  | ProSource |  | FALSE
| FALSE | *** Toto Toilet Add-On | TCST642CEFGAT4001 |  | 1432.563 | Ferguson |  | FALSE
| FALSE | Toilet Washlet + Bidet | TSW4736AT4001 |  | 902.143 | Ferguson |  | FALSE
| FALSE | (2) Sinks Undermount | K-20000-0 |  | 239.58 | Ferguson |  | FALSE
| FALSE | Quartz Top Calacatta Botanica - Square |  |  | 2592 | Cacjr Quartz | 2025-12-11 | FALSE
| FALSE | (2) Faucet & Drain Kit | MT6905ORB |  | 1029.358 | Ferguson |  | FALSE
| FALSE | (2) Faucet Valves | M9000 |  | 239.58 | Ferguson |  | FALSE
| FALSE | Bath Tub Faucet with Handheld | T694ORB |  | 1309.704 | Ferguson |  | FALSE
| FALSE | Bath Tub Rough In | 9792 |  | 333.047 | Ferguson |  | FALSE
| FALSE | [6 empty] | FALSE
Shower & Bath Tile | FALSE | Schulter Kerdi Shower Tray |  | Included |  | ProSource |  | FALSE
Shower & Bath Tile | FALSE | Schulter Shower Curb |  | Included |  | ProSource |  | FALSE
Shower & Bath Tile | FALSE | Schulter Kerdi Right & Left Corners |  | Included |  | ProSource |  | FALSE
| FALSE | Shower Base Tile 15 Sq Ft |  |  |  | ProSource |  | FALSE
| FALSE | Shower Wall Tile 120 Sq Ft |  | 3000 |  |  |  | FALSE
| FALSE | Bath Floor Tile 120 Sq Ft |  | 1500 |  |  |  | FALSE
| FALSE | Tub Deck Area Tile 100 Sq FT |  | 3200 |  |  |  | FALSE
| FALSE | Schulter Edging 32 Linear Ft = 5 pieces |  |  |  | ProSource w/tile |  | FALSE
| FALSE | Quartz caps for shower curb, seat, 3 Shelfs tub wall area and niche All QUARTZ |  |  |  | Cacjr Quartz |  | FALSE
| FALSE | - Grout to match all Smoke Grey - 89 (2 bags) |  |  |  | Floor & Décor |  | FALSE
| FALSE | - Caulk to match all Smoke Grey - 89 |  |  |  | Floor & Décor |  | FALSE
| FALSE | [6 empty] | FALSE
Bathroom Finish Trim | FALSE | 4 1/4" Colonial floor base and shoe molding |  | 1000 |  |  |  | FALSE
| FALSE | Vanity Wall Cabinets |  | 10000 |  | Shiloh |  | FALSE
| FALSE | Quartz Top | [5 empty] | FALSE
| FALSE | Hanging mirror | [5 empty] | FALSE
| FALSE | Moen Voss 24" Towel Bar 2 | YB5124ORB |  | 145.948 | Ferguson |  | FALSE |  | Noted Judy Picked up
| FALSE | Moen Voss Robe Hooks -3 | YB5103ORB |  | 96.954 |  |  | FALSE |  | Left on office
| FALSE | Moen Voss Towel Ring -2 | YB5186ORB |  | 95.7 |  |  | FALSE |  | Counter
| FALSE | Moen Voss Toilet Paper Holder | YB5108ORB |  | 57.079 |  |  | FALSE
Bath Shower Enclose | FALSE | Glass shower door enclosure |  | 2800 |  |  |  | FALSE
FALSE
| FALSE | [6 empty] | FALSE
| FALSE | [6 empty] | FALSE
| FALSE | [6 empty] | FALSE
| FALSE | [6 empty] | FALSE
|  |  |  | 25200 | 14202.038
|  | Allowance |  |  | 25200
-10997.962
*** Add-on Master Toillet Bidet (Lighted Electric outlet)
****Note move exsisting toilet to guest bath

## Kelly, Larry & Sue
Basement Remodeling Selection & Ordering Checklist |  |  |  | General Plumbing Supply (fergusonn out of stock)
| Larry & Sue Kelly 39402-THC | Allowance | Actual Cost | Vendor | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
Island | Custom Shiloh Island |  |  |  |  | FALSE |  | FALSE |  | FALSE
| * Maple Cayenne | 17100 | 4338.36 | Shiloh |  | TRUE | 2025-11-07 | FALSE |  | FALSE
| Quartz Top Full Height Backsplash |  | 10000 | CACJR Granite |  | TRUE | 2025-11-08 | FALSE |  | FALSE
| Note: Not Full Height in Contract $10.00 SQ FT |  |  |  |  | FALSE |  | FALSE |  | FALSE
| *Half Bull Nose RD Corner Overhang Edge |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Cabinet Hardware | 190 | 177.44 | Ferguson |  | TRUE | 2025-11-17 | FALSE |  | FALSE
| * 24 Knobs / 14 Pulls |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| 6" Crown Molding (Travis to get) |  | 300 | Est 5.00 Sq Ft |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Sink - Singel Bowl White Composite | 650 | 533.96 | Ferguson |  | TRUE | 2025-11-08 | FALSE |  | FALSE
| Faucet | 350 | 894.7 | General Plumbing Supply (Ferguson out of Stock) |  | TRUE | 2025-11-07 | FALSE |  | FALSE
| Garbage Disposal Drain |  | 72.77 | Southern Pipe |  | TRUE | 2025-11-10 | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| (1) Dining Table Light Fixtures |  |  |  |  | FALSE |  | FALSE |  | FALSE
| (2) Flush Mount Light Fixtures |  |  |  |  | FALSE |  | FALSE |  | FALSE
| (1) Replace Can with Flush Mount |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
|  | 18290 | 16317.23 |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Total Allowances | 36580

## Cannan, Matthew 39279-LNC
Basement Remodeling Selection & Ordering Checklist
| Matthew & Amy Cannan | Model # | Allowance | Actual Cost | Vendor | Ordered Date |  | Received & Inspected Date |  | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
| Permit |  | 200
Excerise Room | Paint | [5 empty] | FALSE |  | FALSE
| Customer Selected Ceiling | [5 empty] | FALSE |  | FALSE
| Door casing and Floor Base |  | 400 |  |  |  | FALSE |  | FALSE
| Rubber Flooring In add-on |  |  | In Addon Aount | ProSource |  | TRUE |  | FALSE
| Lighting - | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Jack & Jill Bath - Total Allowance $7,200.00
| Shower Valve | U232CIS | 1000 | 198.935 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower 2 handle Trim & Valve | UTS9211BG |  | 622.183 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Head | 3638BG |  | 185.757 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Arm | S122BG |  | 104.885 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Handheld | 220H5BG |  | 301.928 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Handheld Slide Bar | 155746BG |  | 343.354 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Wall Elbow | A725BG |  | 66.55 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Breaker Vacuum | K-9660-2MB |  | 75.768 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Drain (Schulter) | [5 empty] | FALSE |  | FALSE
| Toilet Tank | K-20450-0 |  | 214.632 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Toilet Bowl Skirted | K-20485-0 |  | 358.952 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Toilet Seat | K-26801-0 |  | 58.3 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| 2 Widespread Faucets | TS44102BG |  | 1341.802 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| 2 Widespread Faucets Valves & Drains | M-9000 |  | 254.232 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| 2 Sinks (18" Vanity) | 614000.02 |  | 385.308 | Ferguson | 2025-11-19 | TRUE |  | FALSE
Electric | 2 Vanity Lights |  | 900 |  |  |  | FALSE |  | FALSE
| Exhaust Fan (Service Plus) |  |  |  | Service Plus |  | FALSE |  | FALSE
| Recessed Shower Light (Service Plus) |  |  |  | Service Plus |  | FALSE |  | FALSE
| GFCI Switches outlets and cover plates (Service Plus) |  |  |  | Service Plus |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
J & J Floor Tile | Tile 72 SQ FT 12" x 24" |  | 600 | See TTL ProSource | ProSource | 2025-10-31 | TRUE |  | FALSE
| 3" x 24" Bull Nose Base Board 28 LN FT |  |  | See TTL ProSource | ProSource | 2025-10-31 | TRUE |  | FALSE
| Grout & Caulk | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
J & J Shower Tile | Tile Walls 95 SQ FT 12" x 36" EDEN |  | 1000 | See TTL ProSource | ProSource | 2025-10-31 | TRUE |  | FALSE
| Floor & Niche MSI 1" Mosaic |  |  | See TTL ProSource | ProSource | 2025-10-31 | FALSE |  | FALSE
| Schulter Edge - White to match | [5 empty] | FALSE |  | FALSE
| Quartz Caps |  |  | CACJR Granite |  | 2025-11-21 | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Vanity | 63" Vanity and 2 - 15" |  | 2000 | 4296.81 | WW Woods Shiloh | 2025-11-01 | TRUE |  | FALSE
| Quartz Top Calacatta Botanica / Square |  |  | 1950 | CACJR Granite | 2025-11-21 | TRUE |  | FALSE
| 2 Mirrors | [5 empty] | FALSE |  | FALSE
| Towel Bars | [5 empty] | FALSE |  | FALSE
| Towel Rings | [5 empty] | FALSE |  | FALSE
| TP Holder | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Shower Door | 42" x 76" Shower Door |  | 1800 |  |  |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Master Bath |  |  | 2400 | [5 empty] | FALSE
| Shower Valve | K-8304-KS-NA |  | 126.016 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Head & Trim | K-TS14422-4-BV |  | 699.369 | Southern Pipe | 2025-11-07 | TRUE |  | FALSE
| Diverter Trim | K-T14491-4-BV |  | 286.836 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Diverter Valve | K728-K-NA |  | 204.171 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Hand Held | K-221178-BV |  | 584.54 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Elbow | K-22172-BV |  | 144.243 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Vacuum Breaker | K-9660-BV |  | 75.68 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Drain (Schulter ) | [5 empty] | FALSE |  | FALSE
| Soaker Tub | SH462576 |  | 2056.615 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Soaker Tub Drain Roughin | SH653PVC |  | 216.711 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Soaker Tub Filler w/Diverter | K-T97328-4-BV |  | 2940.35 | Southern Pipe | 2025-11-07 | TRUE |  | FALSE
| Tub Filler Mount | K-97339-NA |  | 177.0937 | Southern Pipe | 2025-11-07 | TRUE |  | FALSE
| 2- Sinks | K-20000-0 |  | 239.58 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| 2 - Faucet & Drain kit | K-14406-BV |  | 1485.5386 | Southern Pipe | 2025-11-07 | TRUE |  | FALSE
| 2 - Faucet & Drain kit | K-14406-BV |  | 892.68 | Supply House | 2025-12-23 | TRUE |  | FALSE
| Toilet Tank | K-20250-0 |  | 214.676 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Skirted Toilet Bowl | K-20485-0 |  | 358.952 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Toilet Seat | K-26801-0 |  | 58.3 | Ferguson | 2025-11-19 | TRUE |  | FALSE
[7 empty] | FALSE |  | FALSE
Electrical | 2 - Exhaust Fans |  | 1500 |  | Service Plus |  | FALSE |  | FALSE
| 4 Wall Sconces | [5 empty] | FALSE |  | FALSE
| Ceiling Light Fixture | [5 empty] | FALSE |  | FALSE
| Shower Recessed Can |  |  |  | Service Plus |  | FALSE |  | FALSE
| 2 Recessed Cans in Bathroom |  |  |  | Service Plus |  | FALSE |  | FALSE
| Light Switches GCFI Plates |  |  |  | Serivice plus |  | FALSE |  | FALSE
Master Floor Tile | Tile: Floor, Shower Walls & Ceiling |  | 2200 | See ProSource TTL | 2025-10-31 |  | TRUE |  | FALSE
Soaker Tub Tile Area | Soaker Tub Area Tile |  | 400 | See ProSource TTL | 2025-10-31 |  | TRUE |  | FALSE
Master Shower Tile | Shower base Tile & Niche 3 x 3 27 Sq Ft |  | 2200 | See ProSource TTL | 2025-10-31 |  | TRUE |  | FALSE
| Bull Nose 156 LN FT |  |  | See ProSource TTL | 2025-10-31 |  | TRUE |  | FALSE
| Grout & Caulk | [5 empty] | FALSE |  | FALSE
| Quartz Caps |  |  | with CACJR |  |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Vanity | 2 - 60" Vanities 2-Towers |  | 3200 | 9482.71 | WW Woods Shiloh | 2025-11-01 | TRUE |  | FALSE
| Quartz Top |  |  | 2960 | CACJR Granite | 2025-11-21 | TRUE |  | FALSE
| 2 Mirrors | [5 empty] | FALSE |  | FALSE
| Towel Bars | [5 empty] | FALSE |  | FALSE
| TP Holder | [5 empty] | FALSE |  | FALSE
Master Shower Glass | Shower Glass |  | 3200
| ProSource Invoice all tile for all rooms |  |  | 7937.89 | ProSource | 2025-10-31
Pink Guest Bath
Electric | Exhaust Fan |  | 300 |  |  |  | FALSE |  | FALSE
Shower Door | 48" x 76" Shower Door |  | 2400 |  |  |  | FALSE |  | FALSE
**Addon Tile Floor - Replace Shower Fixtures, Faucet - Allowanes |  |  | 4500 |  |  |  | FALSE |  | FALSE
| Faucet - Single Handle | M-6903BN |  | 418.231 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Trim | T3691BN |  | 373.021 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Arm | CL10154BN |  | 52.074 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Head | S6365BN |  | 308.594 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Arm Diverter Valve | CL703 BN |  | 106.535 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Handheld | 220H5BN |  | 270.842 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower El | A725BN |  | 65.538 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Vacuum Breaker | K-9660-BN |  | 75.768 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Handheld Slide Bar | K-8524-BN |  | 338.272 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Shower Slide Bar Trim Kit | K-974-BN |  | 53.13 | Ferguson | 2025-11-19 | TRUE |  | FALSE
| Guest Bath Tile Floor |  |  | In ProSource Total | ProSource | 2025-10-31 | TRUE |  | FALSE
| Guest Bath Tile Bull Nose Base |  |  | In ProSource Total | ProSource | 2025-10-31 | TRUE |  | FALSE
| Total Allowances |  | 30000 | 43963.3523
Change Order #1 Guest Bath $14,153.00
| Guest Bath Floor Tile | [8 empty] | 266.48
| Guest Bath Bull Nose Base | [8 empty] | 164.02
Shower Trims & Faucet
Change Order #2 Exercise Room $11,318.00
| Rubber Puzzle Flooring | [8 empty] | 1790.59
Lighting
2221.09
Change Order #3 Basement & Son's Bedroom Paint $8,356.00
Change Order #4 Credit Tuckpointing & Masonry -$9,000.00

## Rhoda, Roberta 39376-CJC
Basement Remodeling Selection & Ordering Checklist
| Roberta Rhoda Bath | Allowance | Actual Cost | Vendor | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
No Permit
[6 empty] | FALSE |  | FALSE |  | FALSE
Bath | SAVE Toilet - RESET |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Faucet | 450 | 716.37 | Ferguson |  | FALSE | 2025-11-11 | FALSE |  | FALSE
| Undermount Sink | 350 | in ferguson order | Ferguson |  | FALSE | 2025-11-11 | FALSE |  | FALSE
| 48 x21 Quartz Back Splash Carrara Breve Edging: Half Bull Nose | 1000 |  | CACJR Granite |  |  | REQ 11/11/25
| 3 New Mirrors for medicine Cabinet | 600 |  | Glass company |  | FALSE |  | FALSE |  | FALSE
| 2 Towel Bars | 100 | in ferguson order | Ferguson |  | FALSE | 2025-11-11 | FALSE |  | FALSE
| Knobs for all cabinets 8 |  | in home depot order | Home Depot |  | FALSE | 2015-11-11 | FALSE |  | FALSE
| T.P. Holder Recesed BN | 50 | 45.01 | Home Depot |  | FALSE | 2015-11-11 | FALSE |  | FALSE
| Towel Ring |  | in ferguson order | Ferguson |  |  | 2025-11-11
Flooring | LVT - Lifeproof Ivory 57 Sq Ft | 350 | 253.51 | Home Depot |  | FALSE | 2015-11-11 | FALSE |  | FALSE
| T-Molding |  | in home depot order |  |  |  |  | FALSE
Cabinet | Utility Broom Closet | 3400 | 4034.52 | Cost 4034.52 |  | FALSE | 2025-10-08 | FALSE |  | FALSE
| Lock for Cabinet | 100 | 62.73 | Rockler (Hinges & Lock) |  |  | 2025-10-03 | FALSE |  | FALSE
| Mirror Hinges |  | w/ Rockler order
Trim | 3 1/4 Colinial Baseboard & Shoe |  |  |  |  | FALSE |  | FALSE |  | FALSE
Painting | Ceiling & Walls
Eletric | Light 4 Blub | 300 | 291.51 | Idlewood Electric |  |  | 2025-11-11
| Exhaust Fan FV-0510VSL1 | 200 | in Feruson Order | Ferguson |  |  | 2025-11-11
ADD On Replace | hand Held In Shower |  |  | 64.42. plus tax |  |  | 2025-11-11
|  | 6900 | 5403.65

## Garwood, Denise Bath
Basement Remodeling Selection & Ordering Checklist
| Denise Garwood Bath | Allowance | Actual Cost | Vendor | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
No Permit
[6 empty] | FALSE |  | FALSE |  | FALSE
Bath | SAVE Toilet - RESET |  |  |  |  | FALSE |  | FALSE |  | FALSE
| SAVE Towel Bar - RESET |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Faucet & Pedestral sink | 300 | 768.64 | Home Depot Ordered |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Lighted Medicine Cabinet | 500 | with sink and faucet | Home Depot ordered |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Flooring | LVT - Lifeproof 25sq est | 200 | 172.3 | HomeDepot Ordered |  | FALSE |  | FALSE |  | FALSE
| Feldstar | [6 empty] | FALSE
Wall tile | Tile on Sink Wall 18 Sq Ft Est | 200 | 683.51 | Home Depot Ordered |  | FALSE | 2025-09-29 | FALSE |  | FALSE
| Tile Edging added for replacing all | [6 empty] | FALSE |  | FALSE
| additional wall tile |  | 512.24 | Home Depot
Trim | 3 1/4 Colinial Baseboard & Shoe | 700 |  |  |  | FALSE |  | FALSE |  | FALSE
Painting | Ceiling & Walls
Shower Door | Adjustable Shower Door 60" EST | 800
|  | 2700 | 2136.69

## Garvin Tom & Laura 39007-THC
Kitchen Remodeling Selection & Ordering Checklist
| Tom & Laura Garvin 39007-THC | Model # | Allowances | Actual Cost | Vendor | Ordered Date |  | Received & Inspected Date | Staging Location | Damaged or Returns Notes
1. Selection Phase (Choosing materials and finishes)
| *** Permit Allowance - |  | 150 |  |  |  | FALSE
FALSE
Kitchen | Allowances $25,910.00 | [5 empty] | FALSE
Cabinets | Cabinet Selection (Material, finish, style) |  | 17450 | 17400 | WW Woods |  | FALSE
| Crown molding on cabinets Small Trim | [5 empty] | FALSE
| Hardware for Cabinets: Quanity | [5 empty] | FALSE
FALSE
Quartz | Countertop - No Backsplash Sparkling White |  | 4700 | 1798 | Cacjr Granite |  | FALSE
| Schulter Edging - | [5 empty] | FALSE
No Backsplash
| Island Counter Stellar White |  |  |  | 1500
| Backsplash Tile MSI Renzo | NRENJAD3X12 GLOSSY | 1200 | 261.3 | ProSource | 2025-10-31 | FALSE
| Grout & Caulk | [5 empty] | FALSE
| Tile Edging | [5 empty] | FALSE
| Sink - |  | 650 | 1041.91 | Ferguson Home | 2025-11-17 | FALSE
| Garbage Disposal Drain |  |  | 48.675 | Ferguson Home | 2025-11-17 | FALSE
| Faucet |  | 500 | 432.3 | Ferguson | 2025-11-17 | FALSE
| Garbage Disposal |  |  | 152.746 | Ferguson | 2025-11-17 | FALSE
| ** R/O Faucet |  |  | 364.34 | Amazon (Out of stock Ferguson) | 2025-11-17 | FALSE
| ** Remove and Reinstall Custome R/O System | [5 empty] | FALSE
FALSE
Flooring | Kitchen Floor LVT Sonia Marble VV872 166 Sq Ft |  | 1410 | 926.21 | ProSource | 2025-10-31 | FALSE
| t-Strip Garage Door | Asked Lou if needed |  |  |  |  | FALSE
| Dining Room Transition Wood Custom | [5 empty] | FALSE
FALSE
Electrical | Light Switches & Outlets per Code | [5 empty] | FALSE
| 7 Recessed Can Lights | [5 empty] | FALSE
| * Fixture over Sink |  |  | 249.73 | Idlewood | 2025-12-05 | FALSE
FALSE
Kitchen Island | All material in Add-on amount | [5 empty] | FALSE
| Cabinets Movable Island |  |  |  | WW Woods |  | FALSE
| Quartz Top - Stellar White Square Edge |  |  |  | CACJR Granite |  | FALSE
| Handles | [5 empty] | FALSE
| Rev-A Shelf for Garbage | [5 empty] | FALSE
| Wheels - | [5 empty] | FALSE
FALSE
Lower Bathroom | Allowances $9,200.00 | [5 empty] | FALSE
Flooring | LVT Coretec Bianco Marble 55 SQ FT |  | 650 | 308.66 | ProSource | 2025-10-31 | FALSE
| matching transition strips-hardwood to lvp @ 6' |  |  | 70.323 | ProSource | 2025-10-31 | FALSE
Shower | Sentrel System |  | 1600 | 1049 | Sentrel (Lou) |  | FALSE
| Shower Base & Drain |  | 1100 | 324.6 | Home Depot (Lou) | 2025-11-18 | FALSE
| Shower Door |  | 1000 | 850.51 | Ferguson Home | 2025-11-17 | FALSE
Vanity | Cabinet Selection (Material, finish, style) |  | 2100 | 2100 | WW Woods |  | FALSE
| Hardware for Cabinets: Quanity | [5 empty] | FALSE
| Quartz Top 42" Soapstone Metropolis Square |  | 850 | 2000 | Cacjr Granite |  | FALSE
| Sink | K-20000-0 | 350 | 119.79 | Ferguson | 2025-11-13 | FALSE
| Faucet | K-22020-4-CP | 400 | 351.428 | Fergusson | 2025-11-13 | FALSE
| Vanity light |  | 350 | 89.96 | Idelwood | 2025-11-21 | FALSE
| Ceiling Light |  |  | 142.56 | Idelwood | 2025-11-21 | FALSE
| Mirror Medicine Cabinet |  | 400 | 439.3 | Ferguson Home | 2025-12-05 | FALSE
| Shower Fixures / Trim | K-TS24617-4-CP | 400 | 108.02 | Ferguson | 2025-11-13 | FALSE
| Shower Fixures / Valve | K-8304-KS-NA |  | 126.016 | Ferguson | 2025-11-13 | FALSE
| Shower Fixture / Head | K-23218-CP |  | 134.365 | Ferguson | 2025-11-13 | FALSE
| Shower Fixture / Arm | K-7397-CP |  | 66.583 | Ferguson | 2025-11-13 | FALSE
| Shower Vacumn | K-9660-CP |  | 47.5 | Ferguson | 2025-11-13 | FALSE
| Grab Bar | K-24550-CP |  | 102.234 | Ferguson | 2025-11-13 | FALSE
| Toilet paper Holder | K-21954-CP |  | 46.882 | Ferguson | 2025-11-13 | FALSE
| Towel Ring | K-21955-CP |  | 35.167 | Ferguson | 2025-11-13 | FALSE
| Towel Bar | K-21953-CP |  | 59.598 | Ferguson | 2025-11-13 | FALSE
| Toilet | K-30810-0 |  | 416.9 | Ferguson | 2025-11-13 | FALSE
FALSE
Upstairs Bath | Allowance $6,750
Flooring | LVT Coretec Iona Stone 90 SQ FT | VV872-12266 | 950 | 463.11 | ProSource |  | FALSE
| matching transition strips-hardwood to lvp @ 6' |  |  | 69.223 | ProSource |  | FALSE
Tub / Shower | Shower Trims |  | 950 |  |  |  | FALSE
| Shower Rod & Curtain | [5 empty] | FALSE
| Shower Fixtures / Tub Spot | K-27422-CP |  | 72.26 | Amazon |  | FALSE
| Shower Fixture / Head | K-23218-CP | 400 | 134.365 | Ferguson | 2025-11-13 | FALSE
| Shower Fixture / Arm | K-7397-CP |  | 66.583 | Ferguson | 2025-11-13 | FALSE
| Shower Trim | K-TS23954-CP |  | 160.248 | Ferguson | 2025-11-13 | FALSE
| Shower Fixures / Valve | K-8304-KS-NA |  | 126.016 | Ferguson | 2025-11-13 | FALSE
| Shower Vacumn | K-9660-CP |  | 47.5 | Ferguson | 2025-11-13 | FALSE
| *** Add-on Toilet | K-30810-0 |  | 416.9 | Ferguson | 2025-11-13 | FALSE
| *** Add on Tub (Cost in addon ) | K-716-0 |  | 0 | Ferguson | 2025-11-13 | FALSE
| *** Add on Tub Drain (Cost in addon ) | K-73213-CP |  | 0 | Ferguson | 2025-11-13 | FALSE
FALSE
Vanity | Cabinet Selection (Material, finish, style) |  | 2100 | 2100 | WW Woods |  | FALSE
| Hardware for Cabinets: Quanity |  |  | 37.3 | Ferguson Home | 2025-12-05 | FALSE
| Sink | K-20000-0 | 350 | 119.79 | Ferguson | 2025-11-13 | FALSE
| Faucet | K-27415-4-CP | 400 | 233.266 | Ferguson | 2025-11-13 | FALSE
| Vanity light |  | 350 | 280.06 | Idlewood | 2025-11-21 | FALSE
| Ceiling Light |  |  | 91.8 | Idlewood | 2025-11-21 | FALSE
| Quartz Top - Fossil Gray |  | 850 | 1800 | Cacjr Granite |  | FALSE
| Mirror SAVE TO CUT DOWN |  | 400 |  |  |  | FALSE
FALSE
| Grab Bar | K-24550-CP |  | 102.234 | Ferguson | 2025-11-13 | FALSE
| Toilet paper Holder | K-27429-CP |  | 50.831 | Ferguson | 2025-11-13 | FALSE
| Towel Bars (3) | K-27426-CP |  | 185.163 | Ferguson | 2025-11-13 | FALSE
FALSE
| ** Add on 2nd Floor Walls - Sentrel Azzura Bay |  | 1600 | 1049 | Sentrel (Lou) |  | FALSE
FALSE
FALSE
Add-on | Change Order #1 Siding, Kitchen Door ProVia | 22281.01 |  |  |  |  | FALSE
| Change Order #2 Permit addtional Costs | 877.5 |  |  |  |  | FALSE
| Change Order #3 2nd Story Bath Shower allowance 1600.00 | 7166 |  |  |  |  | FALSE
| Change Order #4 Island Includes Material | 8402 |  |  |  |  | FALSE
| Change Order #5 Electric Pnael 100 AMP Large and CO2 | 5647 |  |  |  |  | FALSE
Not approved | Change Order #6 Electric AMP 200 Upgrade | 1990 |  |  |  |  | FALSE
Not approved | Change Order #7 Electric Switching Under Cabinet | 1453 |  |  |  |  | FALSE
Not approved | Change Order #8 Plumbing Basement | 3451 |  |  |  |  | FALSE
| Change Order #9 Tub Upper Bath Material & labor | 2541 |  |  |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
| Total Customer Selected Items |  | 43610 | 39270.256

## Conforti, Vince 38894-CJC
Basement Remodeling Selection & Ordering Checklist
| Vince Conforti 38894-CJC | Allowance | Actual Cost | Vendor | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
| Permit | 250
[6 empty] | FALSE |  | FALSE |  | FALSE
Bath Add-ON | [5 empty] | FALSE |  | FALSE |  | FALSE
| Faucet - Ferguson Order |  | 482.78 | Ferguson |  | FALSE | 2025-09-07 | TRUE | 2025-09-25 | TRUE
| Toilet |  |  |  |  | FALSE |  | TRUE | 2025-09-25 | TRUE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Flooring | LVT - Lifeproof Chiffon Lace | 6500 | 4915.55 | Home Depot w/hardware |  | FALSE | 2025-09-07 | TRUE | 2025-09-25 | TRUE
| 14 Stairs |  |  | Home Depot w/hardware |  |  | 2025-09-07 | TRUE | 2025-09-25 | TRUE
Doors | 6 - Panel | 600 | 1295.13 |  |  | FALSE |  | FALSE |  | FALSE
| 3 passage handles Satin Chrome |  | 0 | Home Depot w/hardware |  |  | 2025-09-07 | TRUE | 2025-09-25 | TRUE
| 1 Privacy handle Satin Chrome |  |  | Home Depot w/hardware |  |  | 2025-09-07 | TRUE | 2025-09-25 | TRUE
| 3 hinged door stops |  |  | Home Depot w/hardware |  | FALSE | 2025-09-07 | TRUE | 2025-09-25 | TRUE
| 3 Spring door stop chrome |  |  | Home Depot w/hardware |  |  | 2025-09-07 | TRUE | 2025-09-25 | TRUE
Trim | Door casing, Trim baseboard | 700 | 500 |  |  | FALSE |  | FALSE |  | FALSE
Painting
|  | 8050 | 7193.46

## Schauer, Bill 39372-THC Bath
Basement Remodeling Selection & Ordering Checklist
| Bill & Kathy Schauer | Allowance | Actual Cost | Vendor | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
Hall bath | [5 empty] | FALSE |  | FALSE |  | FALSE
| Shower Base | 900 | 4599.18 | Ferguson |  | FALSE | 2025-10-07 | FALSE |  | FALSE
| Shower Doors | 1500 | Ferguson Order | Ferguson |  | FALSE | 2025-10-07 | FALSE |  | FALSE
| Shower Hand Held and Head | 450 | Ferguson Order | Ferguson |  | FALSE | 2025-10-07 | FALSE |  | FALSE
| Grab Bars - 3 shower, 1 Toilet area | 450 | Ferguson Order | Ferguson |  | FALSE | 2025-10-07 | FALSE |  | FALSE
| *** Toilet SAVE & RESET |  |  |  |  | FALSE | 2025-10-07 | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Vanity 18 x 30 | 1200 | 2876.07 | Shiloh Order |  | FALSE |  | FALSE |  | FALSE
| Additional Wall Doors 5 |  | Cabinet order | Shiloh Order |  | FALSE |  | FALSE |  | FALSE
| Hardware knobs for all |  | 32.4 | Home Depot |  | FALSE | 2025-10-16 | FALSE |  | FALSE
| ***Custom mirror to match | 350 | need mirror cost | Shiloh & Glass Company |  | FALSE |  | FALSE |  | FALSE
| *****Door Front Glass Ready $432.00 |  |  |  |  | FALSE |  | FALSE |  | FALSE
| *****NEED Mirror from Glass Guy |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Quartz Top & shower Pcs. Mystic Gray /white for sill |  | 2150 | CACJR Granite |  | FALSE | 2025-10-27 | FALSE |  | FALSE
| *** Full Bull Nose Extra Charge |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Sink | 450 | Ferguson order | Ferguson |  | FALSE | 2025-10-07 | FALSE |  | FALSE
| Faucet & Drain |  | Ferguson order | Ferguson |  | FALSE | 2025-10-07 | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Tile | Shower Wall Tile 98 SQ Ft | 850 | 1370.84 | ProSource |  | FALSE |  | FALSE |  | FALSE
| Floor Tile 30 SQ FT | 800 | with Wall order | ProSource |  | FALSE | 2025-10-15 | TRUE |  | FALSE
| 5 Pcs Schulter Edging |  | with Wall order | ProSource |  | FALSE |  | FALSE |  | FALSE
| Grout - Mink 25 + 10 lbs |  | 88.52 | Floor & Décor |  | FALSE | 2025-10-16 | FALSE |  | FALSE
| (1) Caulk - Mink |  | Floor & Décor | Floor & Décor |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Towel bars & Toilet Paper |  | Ferguson Order | Ferguson |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Paint | Paint MATCH Light on top / Darker on Bottom |  |  | Sherwin Williams |  | FALSE |  | FALSE |  | FALSE
| Ceiling White |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Chair Rail MATCH Paint MATCH |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
ADD-ON | *** Shower Door Clear Glass |  | 801.5 | Ferguson DEL 11/21 Rush |  | FALSE |  | FALSE |  | FALSE
Main Bath | Quartz - Mystic Gray Full Bull Nose |  | CACJR Granite | CACJR Granite |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Total Allowances to Actual Costs | 6950 | 11918.51 |  |  | FALSE |  | FALSE |  | FALSE
| Allowance |  | -6950 |  |  | FALSE |  | FALSE |  | FALSE
| Over Allowance Materials Add-On |  | 4968.51 |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Total Allowances | 13900

## Marr Barb 38827-THC
Bath Remodeling Selection & Ordering Checklist
| Barb Marr 38827-THC | Allowance | Actual Cost | Vendor | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
| Permit | 150
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Plumbing Fixtures | Sink |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Faucet - Ferguson Order | 1250 | 3789.27 | Ferguson |  | FALSE | 2025-08-06 | FALSE |  | FALSE
| Shower Head | 800 |  |  |  | FALSE |  | FALSE |  | FALSE
| Shower Handle Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Shower Valve |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Shower Transfer Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Shower Transfer Valve |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Hand Held Shower with Rod |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Hand held Wall Elbow |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Hand Held Vacuum Breaker |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Bathtub |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Bathtub Drain |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Toilet Paper Holder |  |  |  |  | FALSE |  | FALSE |  | FALSE
| 2 Hooks |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Towel Bar |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Toilet lever |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Exhaust fan |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Lighted Medicine Cabinet |  |  |  |  | FALSE |  | FALSE |  | FALSE
Electric | Quad Electric Box |  |  |  |  | FALSE |  | FALSE |  | FALSE
Cabinets | Vanity | 2500 | 2898.04 | Teodor Vanities |  | FALSE | 2025-08-09 | FALSE |  | FALSE
Quartz | Vanity Top |  | W/Vanity | Teodor Vanities |  | FALSE | 2025-08-09 | TRUE |  | FALSE
Tile | Shower Walls Tile 24 x 48 | 900 | 1572.93 | ProSource |  | FALSE | 2025-08-05 | TRUE |  | FALSE
| Floor tile 12 x 24 size change | 600 |  | ProSource |  | FALSE | 2025-08-05 | TRUE |  | FALSE
| Grout Dusty Grey & Fossil |  | 102.7 | Floor & Décor |  | FALSE | 2025-08-13 | FALSE |  | FALSE
| Schulter Edging - black 4 |  |  | ProSoure |  | FALSE | 2025-08-05 | TRUE |  | FALSE
| Mirror - Wants lighted Mirror | 200 | 257.6 | Amazon |  |  | 2025-08-12 | X
| medicine Cabinet | 250 | 149.39 | Amazon |  |  | 2025-08-12
Painting
| Exhaust Fan no light | 400 | 100.26 | Ferguson |  |  | 2025-08-18
Add-on
| Light Fixtures | 250 | 377.89 | Idlewood
|  | 7300 | 9248.08

## Brummond, Patty 38867-CJC
Bath Remodeling Selection & Ordering Checklist
|  | Brummond, Patty & Chuck 38867-CJC | Allowance | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | PM / | Lead Jobsite
1. Selection Phase (Choosing materials and finishes)
No Permit Customer Option
|  | Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | TOTAL Allowance | 22600 |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Primary Bath | Vanity w/ Tower 90" | 3500 | 3749.54 | LJA |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Quartz Top |  | 1764 | Celso |  | FALSE |  | FALSE | 2025-08-06 | FALSE |  | FALSE
|  | Handles Knobs |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 2 Faucet - |  | 7195.07 | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | 2 - Sinks Undermount 20" Rec |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | Toilet Comfort Elongated |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower | Valve |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | Valve Trim |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | Diverter Valve & Trim |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | Handheld - Hose |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | Hook for hose |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | Shower Head |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | Drop L |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-29 | FALSE |  | FALSE
|  | Shower Door Semi Frameless 5" |  | 3630.02 | Waukegn Glass Req Options |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Tile Prep | Schulter Pan 3 x 5 Center Drain |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Schulter Drain |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 1 - Bag all set Schulter Mortar |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 2 Rolls Kerdi band 3 x 16.5 |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 1 Schulter Crub 5' |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE
| Tile | 20 Sq FT Shower Floor Tile |  | 2044.74 | ProSource |  | FALSE | 2025-07-06 | FALSE |  | FALSE |  | FALSE
|  | 100 Sq Ft Shower Wall Tile |  |  | ProSource |  | FALSE | 2025-07-06 | FALSE |  | FALSE |  | FALSE
|  | 100 Sq Ft Bath Floor Tile |  |  | ProSource |  | FALSE | 2025-07-06 | FALSE |  | FALSE |  | FALSE
|  | 20 Linear Ft Tile Edge Trim |  |  | ProSource |  | FALSE | 2025-07-06 | FALSE |  | FALSE |  | FALSE
|  | 8 Linear ft Niche Trim |  |  | ProSource |  | FALSE | 2025-07-06 | FALSE |  | FALSE |  | FALSE
|  | 2- 25 Bags of Grout |  | 185.58 | Floor & Décor |  | FALSE | 2025-07-06 | TRUE | 2025-07-09 | TRUE |  | FALSE
|  | 2 - Match Tubes Caulk |  |  | Floor & Décor |  | FALSE | 2025-07-06 | TRUE | 2025-07-09 | TRUE |  | FALSE
FALSE
| Quartz | Vanity Top - |  | 655 | Celso |  | FALSE |  | FALSE | 2025-08-06 | x |  | FALSE
|  | Shower - 6" x 60" Curb |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Knee Wall 6" x 39 Knee Wall Cap |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Niche 4" x 24" |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE
| Electric | 2 Vanity Lights |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Exhaust Fan - No Light |  | 200.52 | Ferguson Home |  | FALSE |  | FALSE | 2025-08-11 | FALSE |  | FALSE
|  | 2- Lights for closet - Flush mount |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| MISC | Moen Folding Shower Seat |  | 246.8 | Amazon |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | TP, Towel Bars, Hooks |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Basement Bath | Vanity 30 " | 950 | 754.18 | LJA |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Handles Knobs |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Faucet - |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Sinks Undermount Rect |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Toilet Comfort Elongated |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Tub/Shower | Tub - 60" x 36" Right Drain |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Valve & Trim |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Head & Escitheon Plate |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Valve & Value Trim |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Tub Spout |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Diverter if Hand held desired |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Hook |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Door | Shower rod
|  | Cabinet / Storage over Toilet |  |  |  |  | FALSE |  | FALSE |  | FALSE
FALSE
|  | 100 Sq Ft Shower Wall Tile |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Tile | 45 Sq Ft Bath Floor Tile |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 45 Linear Ft Tile Edge Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 2- 25 Bags of Grout |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 1- Match Tubes Caulk |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE
| Quartz | Vanity Top 31" x 22" - Right Side splash |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 38 3/4" wide x 2" Deep Window sill |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Niche 4" x 24" |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE
| Electric | 2 Vanity Light |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Exhaust Fan - Picked with Jason |  |  | Ferguson Home |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Lighted Medicine Cabinet |  | 229.48 | Amazon
| MISC | Ceiling Register (CJ will Get) |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | TP, Towel Bars, Hooks |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Closet | LVP LifeProof Brookfield Marble 45 SQ |  |  | Home depot |  | FALSE |  | TRUE |  | FALSE |  | FALSE
| Flooring | 1 Transitions strips reducer carpet to LVP |  |  | Home depot |  | FALSE |  | TRUE |  | FALSE |  | FALSE
| Lighting | 2 Fluch mount Fixtures
| Shelving | Shelving for master closet | [6 empty] | FALSE |  | FALSE
Living Room
| Cabinet | Living Room Custom Cabinet | 10950 | 3543.82 |  |  |  |  | X
Family Room |  | Changed to light fixture vs fan
|  | TTL 38,000.00 | 38000 | 24198.75
Add on |  | basement over the toilet cabinet |  | 698.83
Note on H14: Judy Hogel: Total Ferguson order for all
Note on H33: Judy Hogel: All tile Quote waiting on Final Invoice
Note on H48: Judy Hogel: TTL For both bathrooms

## Jeffrey, Tracy 38729-THC
Kitchen Remodeling Selection & Ordering Checklist
| Tracy Jeffrey 38729-THC | Model # | Allowances | Actual Cost | Vendor | Appointment Dates |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date | Staging Location | Damaged or Returns Notes
1. Selection Phase (Choosing materials and finishes)
| *** Permit Allowance - Note: Permit not figured in CSI total |  | 150 |  |  |  | FALSE |  | FALSE |  | FALSE
| Start Material | [5 empty] | FALSE |  | FALSE |  | FALSE
Plumbing | Refrigerator Water Whip/line | [5 empty] | FALSE |  | FALSE |  | FALSE
| Water Valve Box | [5 empty] | FALSE |  | FALSE |  | FALSE
| Faucet Brushed Nickel - Delta | 9191-AR-PR-DST | 200 | 1462.54 | Ferguson |  | FALSE |  | FALSE | 2025-09-05 | FALSE
| Undermount Sink Single Bowl Kohler | K-28876-NA |  |  | Ferguson |  | FALSE |  | FALSE | 2025-09-05 | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
HVAC | NOTE: Floor registers run thru Toe Kick | [5 empty] | FALSE |  | FALSE |  | FALSE
Electrical | Light Switches & Outlets per Code |  | 500 | 500 | Service Plus |  | FALSE |  | FALSE | CF 9/4/25 | FALSE
| 6 Recessed Can Lightss | [5 empty] | FALSE |  | FALSE |  | FALSE
| Led Under Cabinet Lighting | [5 empty] | FALSE |  | FALSE |  | FALSE
| 8 - Recessed Lights | [5 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
Flooring | LVT 140 SQ Ft |  | 800 | 696.85 | Home Depot |  | FALSE |  | FALSE | 2025-09-04 | TRUE
| 3- matching cap-a-tread @ 45" needed | [5 empty] | FALSE |  | FALSE |  | FALSE
| 1 - matching t-strip | [5 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
Cabinets | Cabinet Selection (Material, finish, style) 42" |  | 15000 | 15000 | LJA Shiloh |  | FALSE |  | FALSE |  | TRUE
| Crown molding on cabinets Small Trim | [5 empty] | FALSE |  | FALSE |  | FALSE
| Hardware for Cabinets: Quanity |  |  | 103.32 | Home Depot (36 Knobs) |  | FALSE |  | FALSE | 2025-09-04 | TRUE
| ** Kitchen Aid Shelf Lift |  |  | 500.5 | ProSource |  | FALSE |  | FALSE | 2025-08-18 | TRUE
Quartz | Countertop - 4" backsplash Carrara Mist |  | 5400 | 2665 | Cacjr Granite |  | FALSE |  | FALSE | 2025-09-05 | TRUE
| Edging - Bevel Edge | [5 empty] | FALSE |  | FALSE |  | FALSE
4" Backsplash
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
Trim | 3 1/4" colonial floor trim and shoe |  | 100 |  | Menards (project) |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
| Appliances ABT to install | [5 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
| Total Customer Selected Items |  | 22000 | 20928.21 |  |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE

## Danta, Andrew 39121-THC
Kitchen Remodeling Selection & Ordering Checklist
| Dennis & Cindy Boiko | Model # | Allowances | Actual Cost | Vendor | Ordered Date |  | Received & Inspected Date | Staging Location | Damaged or Returns Notes
1. Selection Phase (Choosing materials and finishes)
FALSE
| Start Material | [5 empty] | FALSE
Plumbing | Refrigerator Water Whip/line | [5 empty] | FALSE
| Sink - | RVH8310 | 1250 | 511.093 | Ferguson Home | 2025-09-11 | FALSE
| Faucet | 9159-AR-DST |  | 596.255 | Ferguson Home | 2025-09-11 | FALSE
| *Garbage Disposal (not in contract in Service plus) | [5 empty] | FALSE
FALSE
Electrical | Light Switches & Outlets per Code | [5 empty] | FALSE
| LED Light under cabinet | [5 empty] | FALSE
| LED Light in foyer *Service Plus to Supply | [5 empty] | FALSE
FALSE
Flooring | LVT 767 SQ FT H.D. LP Chiffon Lace |  | 4400 | 2937.3322 | Home Depot | 2025-09-11 | TRUE
| matching transition strips-hardwood to lvp @ 6' | [5 empty] | FALSE
Cabinets | Cabinet Selection (Material, finish, style) |  | 13000 | 12900 | LJA Cabinets |  | TRUE
| Crown molding on cabinets Small Trim | [5 empty] | FALSE
| Hardware for Cabinets: Quanity 20 (18) |  |  | 259.52 | Home Depot | 2025-10-28 | TRUE
| Light rail under counters | [5 empty] | FALSE
| **Spice Rack |  |  | 48.7 | Amazon | 2025-10-28 | TRUE
Quartz | Countertop - Full Height backsplash Cararra Breve |  | 8500 | 4800 | Cacjr Granite | 2025-09-09 | TRUE
| Edging - | [5 empty] | FALSE
full Height Back splash
FALSE
Electric | Exhaust fan - Service Plus |  |  |  | Service Plus |  | FALSE
| Foyer Light - Service Plus | [5 empty] | FALSE
FALSE
FALSE
Bath - | Tub divertor Valve in Bath |  |  | 24.6078 | Home Depot | 2025-09-11 | FALSE
FALSE
FALSE
Paint | [6 empty] | FALSE
FALSE
| Total Customer Selected Items |  | 27150 | 22077.508

## Boiko,Dennis 38865-CJC Kitchen
Kitchen Remodeling Selection & Ordering Checklist
| Dennis & Cindy Boiko | Model # | Allowances | Actual Cost | Vendor | Appointment Dates |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date | Staging Location | Damaged or Returns Notes
1. Selection Phase (Choosing materials and finishes)
| *** Permit Allowance - Note: Permit not figured in CSI total |  | 250 |  |  |  | FALSE |  | FALSE |  | FALSE
| Start Material | [5 empty] | FALSE |  | FALSE |  | FALSE
Plumbing | Refrigerator Water Whip/line | [5 empty] | FALSE |  | FALSE |  | FALSE
| Water Valve Box | [5 empty] | FALSE |  | FALSE |  | FALSE
| Sink - Single Bowl |  | 1000 | 637.44 | Ferguson |  | FALSE |  | FALSE | 2025-08-07 | FALSE
| Faucet | [5 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
HVAC | NOTE: Floor registers run thru Toe Kick | [5 empty] | FALSE |  | FALSE |  | FALSE
Electrical | Light Switches & Outlets per Code |  | 200 |  |  |  | FALSE |  | FALSE |  | FALSE
| LED Light Fixture over Island | [5 empty] | FALSE |  | FALSE |  | FALSE
| Flush Mount LED over Sink | [5 empty] | FALSE |  | FALSE |  | FALSE
| 8 - Recessed Lights | [5 empty] | FALSE |  | FALSE |  | FALSE
| Dining Table Fixture / Fan |  |  | 527.04 | Idlewood Electric |  | FALSE |  | FALSE | 2025-08-26 | FALSE
| *Addon - Under Cabinet Bar Lights | [5 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
Flooring | LVT 275 SQ FT H.D. LP Sterling Oak |  | 1300 | 1548.62 | Home Depot |  | FALSE |  | FALSE | 2025-07-17 | FALSE
| 3- matching cap-a-tread @ 45" needed | [5 empty] | FALSE |  | FALSE |  | FALSE
| 2- matching stair noses (overlap) @45" | [5 empty] | FALSE |  | FALSE |  | FALSE
| 2- matching transition strips-hardwood to lvp @ 6' | [5 empty] | FALSE |  | FALSE |  | FALSE
| ** No Charge Addon for Pantry Flooring per Lou | [5 empty] | FALSE |  | FALSE |  | FALSE
Cabinets | Cabinet Selection (Material, finish, style) 42" |  | 14500 | 12760.03 |  |  | FALSE |  | FALSE |  | TRUE
| Crown molding on cabinets Small Trim | [5 empty] | FALSE |  | FALSE |  | FALSE
| Hardware for Cabinets: Quanity 30 |  |  | 378.25 | Hardware Hut |  | FALSE |  | FALSE | 2025-08-21 | TRUE
[7 empty] | FALSE |  | FALSE |  | FALSE
Quartz | Countertop - Full Height Calacatta Botanica |  |  | 5072 | Cacjr Granite |  | FALSE |  | FALSE |  | FALSE
| Edging - Square | [5 empty] | FALSE |  | FALSE |  | FALSE
Possible full Height Back splash - wash in cost
Tile | Backsplash Selection Tile /Changed to full height back splash | [9 empty] | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
| Cabinet Extra Pieces to Hide stairs | [5 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE
| Total Customer Selected Items |  | 17000 | 20923.38
-17000
| Change order #3 Over allowances on Material |  |  | 3923.38

## Briese, Belinda 38875-THC (2)
Bath Remodeling Selection & Ordering Checklist
|  | Allowance | Actual Cost | Vendor | Model # | Appointment Date |  | Selection Complete Date |  |  | Ordered Date |  |  | Received & Inspected Date |  |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
|  | 150 | -150 | Customer does not want Permit
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Plumbing Fixtures |  |  | 1809.66 | Ferguson |  |  | FALSE |  |  | FALSE | 2025-08-05 |  | TRUE |  |  | FALSE
|  |  |  | Ferguson | K-27390-4-CP |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Folding Shower Seat |  | 400 | 266.28 | Amazon | DN-7110 |  | FALSE | 2025-07-24 |  | TRUE | 2025-08-05 |  | TRUE |  |  | FALSE
Shower Pivot Door |  | 2200 | 2741.28 | Waukegan Glass | Swing Door A + Glass Guard |  | FALSE |  |  | FALSE | 2025-08-11 |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Electric Light Fixtures |  | 500 | 420.01 | Idlewood Electric |  |  | FALSE |  |  | FALSE | 2025-08-05 |  | TRUE |  |  | FALSE
Exhaust Fan |  | 350 |  | Ferguson | #VALUE!
Cabinets |  | 1500 | 1541.61 | LJA - Mariola |  |  | FALSE |  |  | FALSE | 2025-07-29 |  | TRUE |  |  | FALSE
Quartz |  |  | 1008 | Cacjr Granite |  |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Medicine Cabinet |  | 350 | 151.54 | Amazon |  |  | FALSE | 2025-07-24 |  | TRUE | 2025-08-05 |  | TRUE |  |  | FALSE
Cabinet Handles |  |  | 49.88 | Home Depot |  |  | FALSE |  |  | FALSE | 2025-08-07 |  | FALSE |  |  | FALSE
Cabinet HAndles Powder Room |  |  | 16.29 | Home Depot |  |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Extra TP Holder NO Charge for install |  |  | 124.29 | Ferguson
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Add-on Allowances |  | 2498
Quartz |  |  | 540 |  |  |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Plumbing Fixtures |  |  |  | Ferguson | K-200000-0 |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
|  |  |  | Ferguson | K-27390-4-CP |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Quartz - carrara Morro |  |  | 435 |  |  |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Plumbing Fixtures |  |  |  | Ferguson | K-200000-0 |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
|  |  |  | Ferguson | K-27390-4-CP |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Hardware Powder Room |  |  |  | Home Depot |  |  | FALSE |  |  | FALSE | 2025-08-10 |  | TRUE |  |  | FALSE
** add-on Amount 2nd story vanity $1,780.00 |  | 630 | 630 | LJA - Mariola |  |  | FALSE |  |  | FALSE | 2025-08-07 |  | FALSE |  |  | FALSE
** add-on Amount Powder Room vanity $1,780.00 |  | 630 | 630 | 630 |  | LJA - Mariola |  |  | FALSE |  |  | FALSE | 2025-08-07 |  | FALSE |  |  | FALSE
|  | 9208 | 10213.84
| Allowance Total |  | -9208
| Total Over Allowances |  | 1005.84
| Contract Price |  | 20799
| Change Order #1 2nd Floor Hall Bath |  | 3698
| Change order #2 Credit Permit |  | -150
| Change Order #3 Vanity 2nd Story |  | 1780
| Change Order #4 Vanity Powder Rm |  | 1780
| Change order #5 for Shower Glass |  | 1347
| Change Order For TP Holders No charge |  | 0
| Change Order #6 Add (2) Light fixtures |  | 945
30199
| Over Allowances Total |  | 1005.84
| Grand Total |  | 31204.84
| Deposit payment 7/11/25 |  | -2500
28704.84

## Briese, Belinda 38875-THC
Bath Remodeling Selection & Ordering Checklist
|  | Allowance | Actual Cost | Vendor | Model # | Appointment Date |  | Selection Complete Date |  |  | Ordered Date |  |  | Received & Inspected Date |  |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
|  | 150 | -150 | Customer does not want Permit
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Plumbing Fixtures |  |  | 1809.66 | Ferguson |  |  | FALSE |  |  | FALSE | 2025-08-05 |  | TRUE |  |  | FALSE
|  |  |  | Ferguson | K-27390-4-CP |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Folding Shower Seat |  | 400 | 266.28 | Amazon | DN-7110 |  | FALSE | 2025-07-24 |  | TRUE | 2025-08-05 |  | TRUE |  |  | FALSE
Shower Pivot Door |  | 2200 | 2741.28 | Waukegan Glass | Swing Door A + Glass Guard |  | FALSE |  |  | FALSE | 2025-08-11 |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Electric Light Fixtures |  | 500 | 420.01 | Idlewood Electric |  |  | FALSE |  |  | FALSE | 2025-08-05 |  | TRUE |  |  | FALSE
Exhaust Fan |  | 350 |  | Ferguson | #VALUE!
Cabinets |  | 1500 | 1541.61 | LJA - Mariola |  |  | FALSE |  |  | FALSE | 2025-07-29 |  | TRUE |  |  | FALSE
Quartz |  |  | 1008 | Cacjr Granite |  |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Medicine Cabinet |  | 350 | 151.54 | Amazon |  |  | FALSE | 2025-07-24 |  | TRUE | 2025-08-05 |  | TRUE |  |  | FALSE
Cabinet Handles |  |  | 49.88 | Home Depot |  |  | FALSE |  |  | FALSE | 2025-08-07 |  | FALSE |  |  | FALSE
Cabinet HAndles Powder Room |  |  | 16.29 | Home Depot |  |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
[7 empty] | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Add-on Allowances |  | 2498
Quartz |  |  | 540 |  |  |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Plumbing Fixtures |  |  |  | Ferguson | K-200000-0 |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
|  |  |  | Ferguson | K-27390-4-CP |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Quartz - carrara Morro |  |  | 435 |  |  |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Plumbing Fixtures |  |  |  | Ferguson | K-200000-0 |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
|  |  |  | Ferguson | K-27390-4-CP |  | FALSE |  |  | FALSE |  |  | FALSE |  |  | FALSE
Hardware Powder Room |  |  |  | Home Depot |  |  | FALSE |  |  | FALSE | 2025-08-10 |  | TRUE |  |  | FALSE
** add-on Amount 2nd story vanity $1,780.00 |  | 630 | 630 | LJA - Mariola |  |  | FALSE |  |  | FALSE | 2025-08-07 |  | FALSE |  |  | FALSE
** add-on Amount Powder Room vanity $1,780.00 |  | 630 | 630 | 630 |  | LJA - Mariola |  |  | FALSE |  |  | FALSE | 2025-08-07 |  | FALSE |  |  | FALSE
|  | 9208 | 10089.55
| Allowance Total |  | -9208
| Total Over Allowances |  | 881.55
| Contract Price |  | 20799
| Change Order 1 2nd Floor Hall Bath |  | 3698
| Change order 2 Credit Permit |  | -150
| Change Order 3 Vanity 2nd Story |  | 1780
| Change Order 4 Vanity Powder Rm |  | 1780
| Change order for Shower Glass |  | 1347
29254
| Over Allowances Total |  | 881.55
| Grand Total |  | 30135.55

## Sayre, Scott 39010-THC Bath
Bath Remodeling Selection & Ordering Checklist
| Scott Sayre - 39010-THC Bath | URL | Allowance | Actual Cost | Vendor | Model # | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | PM / | Lead Jobsite
1. Selection Phase (Choosing materials and finishes)
| Permit Allowance |  | 150
| Start Material Package | [6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[8 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[8 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[8 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[8 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Shower / Tub Fixtures | Moen Multi Function Shower Head / Hand Held | https://www.fergusonhome.com/moen-220c5/s1965009?uid=4649839 | 1200 | 968.05 | Ferguson | 220C5BN |  | FALSE |  | FALSE | 2025-07-25 | TRUE |  | FALSE
| Moen Valve | https://www.fergusonhome.com/moen-2570/s136731?uid=2553010 |  |  | Ferguso n | 2570 |  | FALSE |  | FALSE | 2025-07-25 | TRUE |  | FALSE
| Moen Gibson Tub /Shower Trims | https://www.fergusonhome.com/moen-t2903nh/s1434099?uid=3882444 |  |  | Ferguson | T2903NHBN |  | FALSE |  | FALSE | 2025-07-25 | TRUE |  | FALSE
| Shower Rod |  |  |  | Home Depot
| Delta Classic Tub 60 x 30 | https://www.homedepot.com/p/Delta-Classic-500-60-in-x-30-in-Alcove-Deep-Soaking-Bathtub-with-Left-Drain-in-High-Gloss-White-B23605-6030L-WH/321016480 |  | 834.07 | Home Depot | B23605-6030L-WH |  | FALSE |  | FALSE | 2025-07-25 | TRUE |  | FALSE
[8 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Shower Panel | Sentrel- Azzure Bay |  | 2500 | 1766.64 |  |  |  |  | Lou ordered |  | 2025-06-30
| Niche" 17 x 24 | [6 empty] | FALSE |  | FALSE | 2025-06-30 | FALSE |  | FALSE
[10 empty] | FALSE |  | FALSE
| vanity |  | 2300 | 1078.35 | LJA - Mariola |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Quartz - Calacatta Botanic |  |  | 630 | Celso |  |  | FALSE |  | FALSE | 2025-08-06 | TRUE |  | FALSE
| Knobs |  |  |  | Home Depot |  |  | FALSE |  | FALSE | 2025-07-30 | TRUE |  | FALSE
| 2 - Grab Bars 16/24 |  | 150 |  | Home Deopt |  |  | FALSE |  | TRUE | 2025-07-30 | TRUE |  | FALSE
[8 empty] | FALSE |  | FALSE |  | FALSE
| Electric |  | 200 |  | Home Depot |  |  | FALSE |  | FALSE | 2025-07-30 | TRUE |  | FALSE
[8 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[10 empty] | FALSE |  | FALSE
|  |  | 6350 | 5277.11

## Sommer, Janice 38816-THC shower
Bath Remodeling Selection & Ordering Checklist
| Janice Sommer 38816-THC Tub to Shower Conversion | Allowance | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | PM / | Lead Jobsite
1. Selection Phase (Choosing materials and finishes)
| Permit Allowance | 150
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Shower Fixtures | Shower Head / Hand Held | 450 |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Matte Black | Valve |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Trims |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Shower Door
| Shower Drain |  |  | Menards |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Drain Cover Matte Black |  |  | Menards |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Shower Panel | Sentrel- Azzure Bay |  | 1766.64 |  |  |  | Lou ordered |  | 2025-06-30
| Niche" 17 x 24 |  |  |  |  | FALSE |  | FALSE | 2025-06-30 | FALSE |  | FALSE
[8 empty] | FALSE |  | FALSE
| Shower Base | 650 |  | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Door | 1200 |  | Lowes |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| 2 - Grab Bars 18/24 | 150 | 167.8 | Amazon |  | FALSE | 2025-06-30 | TRUE | 2025-06-30 | TRUE |  | FALSE
| Folding Shower Seat | 400 | 299.86 | Amazon | 2025-06-30 | TRUE | 2025-06-30 | TRUE | 2025-06-30 | TRUE
| Exhaust Fan / With Light | 350 | 179.68 | Amazon |  | FALSE | 2025-06-30 | TRUE | 2025-06-30 | TRUE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[8 empty] | FALSE |  | FALSE
|  | 3350 | 2413.98

## Siragusa 38860-THC Condo B&K
Condo, Kitchen Bath Remodeling Selection & Ordering Checklist
|  | Joy Siragusa 38860-THC | Budgeted Allowance | Purchased | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
| No Permit Figured | [7 empty] | FALSE |  | FALSE |  | FALSE
FALSE
FALSE
| Start Material | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Kitchen | Refrigerator Water Line | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Water Valve Box | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Undermounted Sink |  | 950 |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Faucet | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Kitchen Flooring |  |  | 2800
FALSE
Electrical | [6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[9 empty] | FALSE |  | FALSE |  | FALSE
[9 empty] | FALSE |  | FALSE |  | FALSE
[9 empty] | FALSE |  | FALSE |  | FALSE
[9 empty] | FALSE |  | FALSE |  | FALSE
Kitchen Cabinets | Cabinet Selection (Material, finish, style) |  | 24500 | 32822.82 |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Hardware for Cabinets: Quanity | [7 empty] | FALSE |  | FALSE |  | FALSE
[9 empty] | FALSE |  | FALSE |  | FALSE
Quartz | Countertop Edging: |  | 12000 | [5 empty] | FALSE | 2025-08-05 | TRUE |  | FALSE
| Full Height Back Splash Meridan Gray |  |  | 5200
| Island Different Quartz - Peppercorn White |  |  | 2040 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Living Room |  | USB - USB-C outlets |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Front Closet |  | LED Semi Flush Light with Motion Sensor |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Flooring |  | LVT Flooring Foyer, Front Storage Rm, Living Room, Kitchen & hallway |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Lifeproof Vesinet Oak Wider Plank (returned the smaller plank) |  | 8343.74 | Home Depot |  | FALSE | 2025-07-02 | TRUE | 2025-07-02 | TRUE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Bedroom -1 |  | Ceiling Fan |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Doors |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Bedroom 1 Painting |  | Paint Ceiling, Walls Bedroom 1 |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Bedroom -2 |  | Ceiling Fan |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Doors |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Bedroom 2 Painting |  | Paint Ceiling, Walls Bedroom 2 |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Bedroom -3 Studio |  | Ceiling Fan |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 4 Flush Ceiling Lights on dimmers |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Closet Doors & Pulls/ Cups |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Bedroom 3 Studio Painting |  | Paint Ceiling, Walls Bedroom 3 & Closet |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Add-On Flooring |  | LVT to match the rest | 1800 |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Laundry Room |  | Utilty Sink |  | 327.44 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Faucet |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | New Passage Door |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Knob/Pull |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Laundry Rm Painting |  | Paint Ceiling, Walls Laundry Rm Passage Door |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Hallway Bath |  | Paint Walls & Ceiling |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | New Passage Door |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Knob/Pull |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Interior Doors |  | Shaker Style Solid core | 7200 | 6346.61 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Studio Door Black Metal and Glass Design |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Windows Trim |  | paint only |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Walls |  | Same Color - |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Primary Bath |  | Sink | 360 |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Toilet |  | 259.94 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Faucet |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Head | 700 | 1584.89 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Handle Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Valve |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Transfer Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Transfer Valve |  | 340.44 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Hand Held Shower |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Hand held Wall Elbow |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Hand Held Vacuum Breaker |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Base or Schutler |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Drain |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Shower Door | 2800 |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Toilet Paper Holder | 390 |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Hooks |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Towel Bar |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Exhaust fan |  | 179.68 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Linen Closet & Knobs |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Bath |  | Tile Floor | 3500 | 2669.56 | ProSource |  | FALSE | 2025-06-23 | TRUE | 2025-06-25 | TRUE |  | FALSE
Bath |  | Shower Floor |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Bath |  | Shower Walls |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Bath |  | Grout |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Bath |  | Caulk |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Bath |  | Schulter Edging |  | 71.04 | ProSource |  | FALSE |  | FALSE | 2025-09-04 | FALSE |  | FALSE
Cabinets |  | Vanity, sinks Faucet | 3700 | 3084.82 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Quartz Bath | Bath Vanity and Shower Pieces Carrara Miska or Carrara Breve |  | 1250 | 3500 | Cacjr granite |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Closet | [6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Misc Budget |  |  | 3200 |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Carpet and Install |  |  | 4300 |  | ProSource |  |  |  |  | 2025-06-25 | X
Addons |  | Frame Walls $9,312.00
Flooring in Studio Closet, Walk in $5,826.00
Electric Track Lighting $7,693.00
Additional Track $500.00
Electric Add - on Fans Studio & Living Install 350 *
Hall Bath Light Fixture (Customer Bought) *Not in contract
|  | Hall Bath Toilet (we Purchase 239.99 Costco) *not in contract |  | 259.94
Entry hall Closet Light ( Customer Purchased in contract
Laundry Room Light Customer Purchased *not in contract
|  | 3 Grab Bars in Master *not in Contract |  | 81.38 | Amazon |  |  |  |  | 2025-07-29
1 Grab Bar in Hall Bath by Toilet *Not in contract
Install customer purchased Garbage Disposal *Not in Contract
Tile Bath Ceiling
backsplash change to Pepercorn
|  |  | 69450 | 67112.3
Note on E102: Judy Hogel: Carpet Pad and Tile for Bath
Note on E120: Judy Hogel: Carpet and pad in with tile cost

## Seroogy, Nancy 38718-THC
Kitchen Remodeling Selection & Ordering Checklist
| Nancy Seroogy Steve Gray Kitch 38718-THC | Allowances | Actual Cost | Vendor | Appointment Dates |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date | Staging Location | Damaged or Returns Notes
1. Selection Phase (Choosing materials and finishes)
| *** Permit Allowance - Note: 150.00 | 150 |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Start Material |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Plumbing | Sink | 950 | 419.02 |  |  | FALSE |  | FALSE |  | FALSE
| Fauet |  | 213.88 |  |  | FALSE |  | FALSE |  | FALSE
| Air Switch Garbage Disposal |  | 150.46 |  |  | FALSE |  | FALSE |  | FALSE
Electrical | Light Switches & Outlets Relocate 2 |  |  |  |  | FALSE |  | FALSE |  | FALSE
| * Add- On LED under Cabinet Lighting |  |  |  |  | FALSE |  | FALSE |  | FALSE
| * 2 New Light Fixtures (Cans or Pendants) |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| ** Corner cabinet add-on |  |  |  |  | FALSE |  | FALSE |  | FALSE
Cabinets | Cabinet Selection (Stateville, Alder, White Sands, EDGE 100 | 11250 | 15208.19 | LJA | 3958.19 | FALSE | 2025-07-05 | FALSE |  | FALSE
| *** Corner Wall and Base Angled Cabinet $3,310.42 |  | 3310.42
| Crown Molding - Only on corner 42" |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Hardware for Cabinets: Quanity 34 |  | 85.27 | Home Depot |  | FALSE |  | FALSE | 2025-08-07 | TRUE
| ** Light Strip Corner Cabinet |  | 84 | LJA |  | FALSE |  | FALSE | 2025-08-10 | FALSE
| electric for Light strip |  | 350 | SP - Approved
Quartz | Countertop - |  | 6400 | Estimate of highest |  | FALSE |  | FALSE |  | FALSE
| Edging - half Bull Nose (possible full bull knose on passthrough |  |  |  |  | FALSE |  | FALSE |  | FALSE
| backsplash Tile - |  | 354.62 | Lowes |  | FALSE |  | FALSE |  | FALSE
| Grout & Cauld Natural Grey - P-UP Addiosn |  | 51.47 | Floor & Décor |  | FALSE |  | FALSE | 2025-08-14 | FALSE
Counter | Counter: Pass-thru Butcher Block CHG to Quartz |  |  |  |  | FALSE |  | FALSE |  | FALSE
Stain Color:
[6 empty] | FALSE |  | FALSE |  | FALSE
Flooring | ** CHANGE TO Just laundry room LVT Kitchen, Sunroom, Hallway & Laundry Room | 4200 | 329.77 |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Painting | Kitchen & Adjacent Hallway Ceiling & Walls |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Main Bath | * Customer Supplied Shower Door |  |  |  |  | FALSE |  | FALSE |  | FALSE
| * Customer Supplied Light Fixtures |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Paint Walls |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Total Customer Selected Items | 16550 | 26957.1
| *** Add-On Wall Removal Header / No Post | 7989
** Credit - Floor replaced $4,200 in material
*** Laundrey Room Flooring replaced with LifeProof
Per 7/17/25 Meeting with Lou and Jeremy - Contract Price - Flooring
Contract to be orignial price with only $950.00 in Allowance left - Any changes after that are addon's
*** $80.00 + $350.00 for Light Rail on Corner Cabinet Approved 8/10
Approved Air Switch
Per meetin

## Dunne, Nancy 38896-THC
Bath Remodeling Selection & Ordering Checklist
| Nancy Dunne 38896-THC Master Bath | Allowances | Purchased | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
Permit | Allowance $150.00 | 150 | -150 | Customer paid in person (issue Credit | [5 empty] | FALSE |  | FALSE
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Plumbing Fixtures | Soaker Tub, Drain, | 2100 | 4995.64 | Ferguson |  | FALSE | 2025-07-06 | TRUE | 2025-07-07 | TRUE |  | FALSE
| Soaker Tub Faucet |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-07 | TRUE |  | FALSE
| Sink |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-07 | TRUE |  | FALSE
| Faucet |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-07 | TRUE |  | FALSE
| Shower Head |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-07 | TRUE |  | FALSE
| Shower Handle Trim |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-07 | TRUE |  | FALSE
| Shower Valve |  |  | Ferguson |  | FALSE |  | FALSE | 2025-07-07 | TRUE |  | FALSE
| Shower Base Schulter Tile |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Drain |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Door /Glass + Protected Coating | 3000 | 2365.98 | Waukegan Glass |  | FALSE |  | TRUE |  | FALSE |  | FALSE
| Toilet |  |  | Ferguson |  | FALSE |  | TRUE | 2025-07-07 | TRUE |  | FALSE
| Toilet Paper Holder |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| 3 - Towel Bar |  | 76.6 | Home Depot |  | FALSE |  | FALSE | 2025-08-08 | TRUE |  | FALSE
| Shower Grab Bar |  | 46.42 | Amazon |  | FALSE |  | FALSE | 2025-07-07 | TRUE |  | FALSE
| Folding Shower Seat |  | 246.79 | Amazon |  | FALSE |  | FALSE | 2025-07-07 | TRUE |  | FALSE
Electric | Vanity Light | 1000 | 488.75 | Idlewood Electric |  | FALSE |  | FALSE | 2025-08-14 | TRUE |  | FALSE
| Bath Flush Center light |  |  | Idlewood Electric |  | FALSE |  | FALSE | 2025-08-14 | TRUE |  | FALSE
| Exhaust fan no light |  | 102.83 | Amazon |  | FALSE |  | FALSE | 2025-08-08 | TRUE |  | FALSE
* Shower Recessed light & Switch NO SHOWER LIGHT
* GFI Outlets & Switches
Cabinets | Vanity | 3100 | 2738.15 | Shiloh |  | FALSE |  | TRUE | 2025-07-04 | TRUE |  | FALSE
Quartz | Quartz Vanity Top & Shower Curb |  | 1242 | Cacjr Granite |  | FALSE |  | TRUE | 2025-08-04 | TRUE |  | FALSE
| Quartz For Pony Wall | 250
Tile | Shower Walls | 1800 | 1655.56 | ProSource |  | FALSE |  | FALSE | 2025-07-30 | TRUE |  | FALSE
| Shower Floor | 150 |  | ProSource |  | FALSE |  | FALSE | 2025-07-30 | TRUE |  | FALSE
| Bath Tile Floor | 1200 |  | ProSource |  | FALSE |  | FALSE | 2025-07-30 | TRUE |  | FALSE
| Schulter Edging brushed Nickle order with tile |  |  | ProSource |  | FALSE |  | FALSE | 2025-07-30 | TRUE |  | FALSE
| Grout Will decide once tile there |  |  | Floor & Décor |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Caulk |  |  | Floor & Décor |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Painting | Paint Walls: some shade of white |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 12750 | 13808.72
| Add-on Shower moved (Quartz & Door) | 2647

## Brann 38849-CJC Laundry & Bath
Bath & Laundry Room Remodeling Selection & Ordering Checklist
|  | Diana Brann 38849-CJC | Allowance | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | PM / | Lead Jobsite
1. Selection Phase (Choosing materials and finishes)
|  | Permit *Allowance $250.00 | 250
|  | Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Bath |  | Vanity, Sink Combo | 1200 | 3088.3 | Home Depot | 2025-05-29 | TRUE | 2025-05-29 | TRUE | 2025-06-04 | TRUE |  | FALSE
** NOTE:Mega to make Filler Painted to match
|  | Faucet - Brushed Nickel |  |  | Home Depot | 2025-05-29 | TRUE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
|  | Toilet Toto Elongated | 800 |  | Home Depot | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
|  | Toto Washlet |  |  | Home Depot | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
| Extra ** | 4 - Knobs for Vanity Brushed Nickel |  |  | Home Depot | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
|  | Shower Trim | 350 | 1684.2 | Ferguson | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-06 | TRUE |  | FALSE
|  | Shower Valve |  |  | Ferguson | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-06 | TRUE |  | FALSE
|  | Shower Head/Hand Held Combo |  |  | Ferguson | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-06 | TRUE |  | FALSE
|  | Exhust Fan NO light | 350 |  | Amazon | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
|  | Medicine Cabinet | 150 |  | Home Depot | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
|  | Vanity Light | 150 |  | Home Depot | 2025-05-29 | FALSE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
|  | Sentrel Panel Veincut Grey | 2400 |  | Lansing | 2025-05-29 | FALSE | 2025-06-02 | FALSE |  | FALSE |  | FALSE
|  | Sentrel Cubby 17 x 26 |  |  |  | 2025-05-29 | FALSE | 2025-06-02 | FALSE |  | FALSE |  | FALSE
|  | Sentrel Shower Base Veincut Grey | 850 |  |  | 2025-05-29 | FALSE | 2025-06-02 | FALSE |  | FALSE |  | FALSE
Flooring |  | LVP LifeProof Ashen Grove (12) |  |  | Home Depot | 2025-05-29 | TRUE | 2025-05-29 | TRUE | 2025-06-04 | TRUE |  | FALSE
Flooring |  | 1 Transitions strips reducer carpet to LVP |  |  |  | 2025-05-29 | TRUE | 2025-05-29 | TRUE | 2025-06-04 | TRUE |  | FALSE
Laundry Room |  | Drop Ceiling $3.00 SQ FT |  |  | Home Depot | 2025-05-29 | TRUE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
|  | 60 X 80 Hollow Core Bi-Fold Pantry | 350 |  |  |  | TRUE |  | TRUE |  | FALSE |  | FALSE
|  | Fold down Laundry Folding Table | 300 | 110.52 | menards | 2025-05-29 | TRUE | 2025-06-02 | TRUE | 2025-06-23 | FALSE |  | FALSE
|  | Fold Down Drying Rack |  | 60.61 | Amazon | 2025-05-29 | TRUE |  | TRUE | 2025-06-23 | TRUE |  | FALSE
|  | laundry Sink Faucet Combo | 400 |  | Home Depot | 2025-05-29 | TRUE | 2025-06-02 | TRUE | 2025-06-04 | TRUE |  | FALSE
|  | LED 2 x 4 Panel Light |  |  | Home Depot |  | FALSE |  | FALSE | 2025-06-06 | TRUE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Hall |  | Drop Ceiling |  |  |  | 2025-05-29 | FALSE | 2025-05-29 | TRUE |  | TRUE |  | FALSE
Hall |  | 60 x 80 Hollow Core Bi-Fold Closet Doors |  |  | Menards | 2025-05-29 | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | Pull Knobs - 2 |  |  |  | 2025-05-29 | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
|  |  | 7300 | 4943.63

## Hyett HZR1 38537-LNC
Bath Remodeling Selection & Ordering Checklist
| Kendra Hyett 38537-LNC | Purchased or Estimated | Vendor | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
[5 empty] | FALSE |  | FALSE
| Start Material Package |  |  |  | FALSE |  | FALSE
Workout Room | Cork Underlayment Flooring |  |  |  | FALSE |  | FALSE
| Rubber Flooring Tile |  |  |  | FALSE |  | FALSE
| LVP in Storage Area |  |  |  | FALSE |  | FALSE
| Handles for Storge Doors |  |  |  | FALSE |  | FALSE
| Cabinets for Workout Room |  | ProSourcce | 2025-05-28 | FALSE |  | FALSE
| Cabinets Handles Matte Black |  |  |  | FALSE |  | FALSE
| Mini Frig | 1490.41 | ABT |  | FALSE |  | FALSE
| Quartz Counter Top to Match bath |  |  |  | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE
Bedroom | Carpet & Padding | 15161.95 |  |  | FALSE |  | FALSE
| Area Rug | 5000 |  |  | FALSE |  | FALSE
| Doors |  |  |  | FALSE |  | FALSE
| Trim |  |  |  | FALSE |  | FALSE
Bedroom Painting | Paint Walls Bedroom
[5 empty] | FALSE |  | FALSE
Plumbing Fixtures | 2 -Sink | 17867.07 | Ferguson | 2025-05-31 | FALSE |  | FALSE
| 2 - Faucet Matte Black |  | Ferguson | 2025-05-31 | FALSE |  | FALSE
| Shower Head |  | Ferguson | 2025-05-31 | FALSE |  | FALSE
| Shower Handle Trim |  | Ferguson | 2025-05-31 | FALSE |  | FALSE
| Shower Valve |  | Ferguson | 2025-05-31 | FALSE |  | FALSE
| Shower Transfer Trim |  | Ferguson | 2025-05-31 | FALSE |  | FALSE
| Shower Transfer Valve |  | Ferguson | 2025-05-31 | FALSE |  | FALSE
| Hand Held Shower |  | Ferguson | 2025-05-31 | FALSE |  | FALSE
| Hand held Wall Elbow |  | Ferguson | 2025-05-31 | TRUE |  | FALSE
| Hand Held Vacuum Breaker |  | Ferguson | 2025-05-31 | TRUE |  | FALSE
| Shower Base or Schutler |  | Ferguson | 2025-05-31 | TRUE |  | FALSE
| Shower Drain Matte Black |  | ProSource | 2025-05-31 | TRUE |  | FALSE
| Shower Door - Custom |  | Waukegan Glass |  | FALSE |  | FALSE
| Toilet Paper Holder |  | Ferguson | 2025-05-31 | TRUE |  | FALSE
| Hooks |  | Ferguson | 2025-05-31 | TRUE |  | FALSE
| Towel Bar |  | Ferguson | 2025-05-31 | TRUE |  | FALSE
| Toilet lever |  | Ferguson | 2025-05-31 | TRUE |  | FALSE
| Exhaust fan | 102.83 | Amazon | 2025-06-12 | TRUE |  | FALSE
[5 empty] | FALSE |  | FALSE
Bath | Tile Floor | 4731.03 | ProSource | 2025-06-12 | TRUE |  | FALSE
Bath | Shower Floor |  | ProSource | 2025-06-12 | TRUE |  | FALSE
Bath | Shower Walls |  | ProSource | 2025-06-12 | TRUE |  | FALSE
Bath | Grout | 188.57 | Floor & Décor | 2025-07-08 | FALSE |  | FALSE
Bath | Caulk |  |  |  | FALSE |  | FALSE
Bath | Schulter Edging |  | ProSource |  | TRUE |  | FALSE
Electric | Vanity Lights (2) 3l light (1) 2 light | 517 | Littman Bros | 2025-06-06 | FALSE |  | FALSE
| Bath Fixture | 566.5 | Littman Bros | 2025-06-11 | FALSE |  | FALSE
| Bath Makeup Mirror | 584.45 | Lamps Plus | 2025-06-02 | FALSE |  | FALSE
| Closet Light Fixture - |  |  |  | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE
heated Floor | Warmly Yours Heated Floor | 1200.06 |  | 2025-06-02 | X
Cabinets | Vanity | 15705.8 | ProSource Omega | 2025-02-28 | TRUE |  | FALSE
Knobs | 9 Knobs 10 Pulls | 6141 | ProSource Top Knobs | 2025-06-13 | X
Shower Door |  | 4637.42 | Waukegan Glass | 2025-07-17
Quartz | Vanity Top, Shower Niche, Sill, Curb? |  | Celso | 2025-06-14 | TRUE |  | FALSE
Calacatta Miraggo Cove
[5 empty] | FALSE |  | FALSE
Closet | Closet Cabinets - All handles, Bars Trim | 34411 | Closets By Design | 2025-05-31 | TRUE |  | FALSE
| Grout |  |  |  | FALSE |  | FALSE
| Caulk |  |  |  | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE
Painting | Paint Walls Workout Room
Painting | Paint Walls Closet
Painting | Paint Walls Bathroom
Painting | Paint Walls Bedroom
108305.09

## Houser 38753-THC Bath
Bath Remodeling Selection & Ordering Checklist
| Houser 38753 | Allowance | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | PM / | Lead Jobsite
1. Selection Phase (Choosing materials and finishes)
No Permit Customer Option
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Plumbing Fixtures | Vanity Top with Sink |  |  | Menards |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Faucet - |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Toilet comfort Round and floor | 350 | 562.79 | Home Depot |  | FALSE | Lou ordered | FALSE | Lou Ordered | TRUE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Cabinets | Vanity 48" X 21" | 1800 | 1158.42 | Menards |  | FALSE | 2025-05-20 | TRUE | 2025-05-20 | TRUE |  | FALSE
| Handles - |  | 43.32 | Home Depot |  |  | 2025-05-20 | TRUE | 2025-05-20 | TRUE
| Side splash |  | 32.69 |  |  |  | 2025-05-20 |  | 2025-05-20
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
|  |  |  | Home Depot |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Flooring | LVP LifeProof Brookfield Marble 45 SQ |  |  | Home depot |  | FALSE |  | FALSE | Lou Ordered | TRUE |  | FALSE
Flooring | 1 Transitions strips reducer carpet to LVP |  |  | Home depot |  | FALSE |  | FALSE |  | TRUE |  | FALSE
[8 empty] | FALSE |  | FALSE
|  | 2150 | 1797.22

## Dahlstrom 38873-THC
Bath Remodeling Selection & Ordering Checklist
| Terry Dahlstrom 38873-THC | Allowance | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | PM / | Lead Jobsite
1. Selection Phase (Choosing materials and finishes)
No Permit Customer Option
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Electric | 2 light fixtures Main | 300 | 448.16 | lamps Plus |  | FALSE |  | FALSE | 2025-07-07 | TRUE
| 2 Lights hall bath | 300 | 231 | Littman Bros | [5 empty] | x
Mirror | 2 Main Bath Wall hanging mirrors | 300 | 227.3 | Amazon |  | FALSE |  | FALSE |  | TRUE |  | FALSE
| Hall Bath |  | 82.95 | Home Depot |  |  |  | FALSE |  | TRUE
Faucet | Sink main Bath |  | 86.25 | Home dpeot | [5 empty] | x
| Faucet Main Bath | 550 | 244.68 | Fergguson |  | FALSE |  | FALSE |  | TRUE |  | FALSE
| light blubs |  | 29.46 | Home Depot | [5 empty] | x
Doors | 24" Bifold Closet Doors - White |  |  |  |  | FALSE |  | FALSE |  | TRUE |  | FALSE
Flooring | LVP |  |  |  |  | FALSE |  | FALSE |  | TRUE |  | FALSE
Flooring | T-Strip |  |  |  |  | FALSE |  | FALSE |  | TRUE |  | FALSE
Painting | [7 empty] | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 1450 | 1349.8
** Add-on Exhaust Fan in Main Bath |  |  | 179.59

## VonRentzell - 38725-THC Bath
Bath Remodeling Selection & Ordering Checklist
| Jeanne VonRentzell 38725-THC | Allowance | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | PM / | Lead Jobsite
1. Selection Phase (Choosing materials and finishes)
No Permit Customer Option
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
|  |  | estimate |  |  | TRUE |  | FALSE |  | FALSE |  | FALSE
Plumbing Fixtures | Sink | 1500 | 471.82 | Home Depot |  | TRUE | 2025-05-25 | TRUE | 2025-05-27 | TRUE |  | FALSE
| Faucet - Chrome no spill |  | w/hd | Home Depot |  | TRUE | 2025-05-25 | TRUE | 2025-05-27 | TRUE |  | FALSE
| Insides of kohle toilet |  | 19.27 | Menards | Travis | TRUE |  | TRUE |  | TRUE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Electric | Light Switch / GFI Outlet |  | 22.47 | Menards | Travis | FALSE |  | FALSE |  | TRUE
Cabinets | Vanity 21 x 18" 34 1/2 tall | 1500 | 500 | ProSource |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Handle 1 |  | w/ hd | Home Depot |  |  | 2025-05-25 | TRUE | 2025-05-27 | TRUE
Quartz | Vanity Top |  | 250 | Cacjr Granite | Email options 5/25 | FALSE |  | FALSE |  | FALSE |  | FALSE
| HVAC Vent Cover |  | 12.76 | Menards Travis |  | FALSE |  | TRUE |  | TRUE |  | FALSE
Flooring | LVP 30 SQ Ft |  | with HD order | Home depot |  | FALSE | 2025-05-25 | TRUE | 2025-05-27 | TRUE |  | FALSE
Flooring | 3 Transitions strips |  | w/ HD | Home depot |  | FALSE | 2025-05-25 | TRUE | 2025-05-27 | TRUE |  | FALSE
[8 empty] | FALSE |  | FALSE
|  | 3000 | 1276.32

## Roloff 38562-LNC Basement
Basement Remodeling Selection, Ordering & Receiving Checklist
Christine Roloff 38563-LNC |  | bath floor & shower walls) | Allowances | Actual Cost | Vendor | Appointment Date |  | Ordered Date |  | Received & Inspected Date
1. Selection Phase (Choosing materials and finishes)
| FALSE | *** Permit Allowance - | 150 | 2900.4 |  |  | FALSE |  | TRUE
Electrical - Reccessed all | FALSE | 33 - LED recessed lights (18 for open area, 6 for dance room, 9 for media room) | 3700 | 1414 |  |  | FALSE |  | TRUE
Electrical - Bath | FALSE | Bath Exhusted Fan |  |  | Amazon |  | FALSE | 2025-05-03 | TRUE
Electrical - Bath | FALSE | Bath Vanity Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bath | FALSE | Recessed Shower Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bath | FALSE | 4 Bath Switches |  |  |  |  | FALSE |  | FALSE
Electrical - Dance | FALSE | Dance Room 6 Recessed Lights |  |  |  |  | FALSE |  | FALSE
Electrical - Dance | FALSE | Dance Room closet Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bedroom | FALSE | Bedroom Fan 42" |  |  | Home Depot | 2025-05-20 | TRUE | 2025-05-22 | TRUE
Electrical - Bedroom | FALSE | Bedroom Closet Light - Motion Sensored |  |  | Home Depot |  | FALSE |  | FALSE
Electrical - Bedroom | FALSE | 3 Light Switches |  |  |  |  | FALSE |  | FALSE
Electrical - Media | FALSE | Cabinet Lighting (next to fireplace) |  |  |  |  | FALSE |  | FALSE
Electrical - Wet Bar | FALSE | Cabinet Lighting under and inside wall cabinets |  |  |  |  | FALSE |  | FALSE
| FALSE | Electric Outlets for all areas |  |  |  |  | FALSE |  | FALSE
| FALSE | ** 50" Fan Media Room |  |  | Home Depot | 2025-05-20 | TRUE | 2025-05-22 | TRUE
Flooring - Open Area | FALSE | Coretec Luxury Vinyl Plank (LVP) flooring – 1,000 sq. ft. | 5000 | 7039.26 |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | 3 Coretec Carpert Reducers |  |  |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | 2 Coretec T-Molding |  |  |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
Flooring - Bedroom & Closet | FALSE | Carpet and padding (for bedroom and closet) 280 SQ Ft | 2500 | 1024.21 |  | 2025-04-29 | TRUE | 2025-04-30 | FALSE
Flooring - Dance Room & Closet | FALSE | Pre-finished oak flooring (for dance room and closet) | 1400 | 4970 | Material 3616.20 Mr Floor |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Painting - Open Area Ceiling | FALSE | Spray Ceiling to unfinished ceiling framing, mechanicals & HVAC | Included |  |  |  | FALSE |  | FALSE
Painting - Dance Room | FALSE | Spray Ceiling to unfinished ceiling framing, mechanicals & HVAC | Included |  |  |  | FALSE |  | FALSE
Painting - Bathroom | FALSE | Paint Ceiling, Walls, Door & Trim | Included |  |  |  | FALSE |  | FALSE
Painting - Bedroom | FALSE | Paint Ceiling, Walls, Closet, Doors, & Trim | Included |  |  |  | FALSE |  | FALSE
Painting - Media Room | FALSE | Paint Ceiling, Wall, Floor Base, Shoe Mold, Door Jamb and Casing | Included |  |  |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Finish Trim - Open, Media, 3 Closets | FALSE | Pre-hung Primed 6-panel doors: Unders Stairs, Walk-in, Furnace & Sump Pump | 2800 | 4500.65 |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | (4) - Lock Sets for Doors and Closets |  | 400.28 |  |  | FALSE |  | FALSE
| FALSE | Window jambs and casing |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  | 2750 |  |  | FALSE |  | FALSE
| FALSE | 30' Wire shelves for closets (Lou to order) |  | 429.99 | Home depot aLL CLOSETS |  | FALSE | 2025-08-25 | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Bathroom Plumbing | FALSE | Shower Valve | 2300 | 2423.39 | Ferguson | 2025-04-29 | TRUE | 2025-05-21 | TRUE
| FALSE | Shower Head |  |  |  |  | FALSE | 2025-05-21 | TRUE
| FALSE | Schulter Shower Drain Kit |  |  |  |  | FALSE | 2025-06-05 | TRUE
| FALSE | Toilet |  | 1181.64 | Home Depot (fans, Toiliet ) Handles Door Stops |  | FALSE | 2025-05-22 | TRUE
| FALSE | Toilet Kohler Flush handle Matte Black |  |  | Home Depot |  | FALSE | 2025-05-22 | TRUE
| FALSE | Water valve, wax ring, and water line |  |  |  |  | FALSE |  | FALSE
| FALSE | Sink (Note: Not in contract) |  |  | Ferguson |  | FALSE | 2025-05-21 | TRUE
| FALSE | Quartz Top |  |  | Crajr Granite | 2025-04-30 | FALSE | 2025-05-29 | TRUE
| FALSE | Faucet & Drain Kit |  |  | Ferguson |  | FALSE | 2025-05-21 | TRUE
| FALSE | Exhaust Fan with Light |  | 179.68 | Amazon |  | FALSE | 2025-05-03 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Shower & Bath Tile | FALSE | Schulter Kerdi Shower Tray 36 x 48 | Included |  | ProSource |  | TRUE | 2025-04-30 | TRUE
Shower & Bath Tile | FALSE | Schulter Shower Curb 48" x 36" | Included |  | ProSource |  | TRUE | 2025-04-30 | TRUE
Shower & Bath Tile | FALSE | Schulter Kerdi Right & Left Corners | Included |  | ProSource |  | TRUE | 2025-04-30 | TRUE
Flooring - Bathroom | FALSE | Radiant Heat Mat (lou to order) |  | 736.23 | Warmly Yours |  | FALSE | 2025-07-16 | TRUE
| FALSE | Shower Base Tile 15 Sq Ft | 2500 | 1486.96 | ProSource | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | Shower Wall Tile 120 Sq Ft (ordered 171.6 SQ FT for Bath floor& shower walls) |  |  |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | Bath Floor Tile 50 Sq Ft | 700 |  |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | Schulter Edging 32 Linear Ft = 5 pieces |  |  | ProSource w/tile |  | FALSE | 2025-04-30 | TRUE
| FALSE | Quartz caps for shower curb, seat 12" x 18" , and niche All QUARTZ |  |  | Cacjr Quartz |  | FALSE | 2025-05-20 | TRUE
| FALSE | 50 LBS - Grout to match all Smoke Grey - 89 (2 bags) |  | 101.07 | Floor & Décor | 2025-04-29 | TRUE | 2025-05-22 | TRUE
| FALSE | 2 - Caulk to match all Smoke Grey - 89 |  |  | Floor & Décor | 2025-04-29 | FALSE | 2025-05-22 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
Bathroom Finish Trim | FALSE | Pre-hung Primed 6-panel door | 3000 |  |  |  | FALSE |  | FALSE
| FALSE | Primed 6 panel Pocket Door Slab |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | (1) - Lock Sets for Door |  | 31.9 | Home Depot | 2025-05-22 | FALSE | 2025-08-26 | FALSE
| FALSE | Pocket Door Hardware |  |  |  |  | FALSE |  | FALSE
| FALSE | 2 Bi-Pass Cups Matte Black |  |  | Home Depot | 2025-05-22 | FALSE |  | FALSE
| FALSE | 36" Vanity Cabinet |  | cabinet order | ProSource | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | Quartz Top |  |  | Cacjr Quartz |  | FALSE | 2025-05-30 | TRUE
| FALSE | Hanging mirror |  | 85.51 | Amazon |  | FALSE | 2025-05-19 | TRUE
| FALSE | Kohler Numista 3 piece Bath set |  | 133.52 | Home Depot | 2025-04-29 | TRUE | 2025-05-02 | TRUE | 2025-05-19 | Noted Judy Picked up
| FALSE | Kohler Numista Robe Hook |  |  | Home Depot | 2025-04-29 | TRUE | 2025-05-02 | TRUE | 2025-05-19 | Left on office
| FALSE | Kohler Numista 18" Towel Bar |  |  | Home Depot | 2025-04-29 | TRUE | 2025-05-02 | TRUE | 2025-05-19 | Counter
| FALSE | Bath Vanity Liight |  | 121 | Littman Bros |  | FALSE | 2025-06-06 | FALSE
| FALSE | Lights, toilet, toilet handle, cabinet handles, Door stops |  | 719.02 | Home Depot |  | FALSE | 2025-05-22 | TRUE
| FALSE | 14 Spring Door Stops - white |  |  | Home Depot |  | FALSE | 2025-05-22 | TRUE
| FALSE | 10 - Hinges Door Stops - White |  |  | Home Depot |  | FALSE | 2025-05-22 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Bath Shower Encloser | FALSE | Glass shower door enclosure (60”x76”) | 3400 | 3294.06 | Waukegan Gurnee Glass Company |  | FALSE |  | TRUE
[7 empty] | FALSE |  | FALSE
Bedroom & Closet Finish Trim | FALSE | Window Jams 3 1/2' Primed Colonial Casing | 1200 |  |  |  | FALSE |  | FALSE
| FALSE | 2 - Pre-hung Primed 6-panel door |  |  |  |  | FALSE |  | FALSE
| FALSE | Primed 6 panel Pocket Door Slab |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | (2) - Lock Sets for Doors |  |  | Home Depot | 2025-05-20 | TRUE |  | FALSE
| FALSE | 16 LN FT of Wire White Shelving |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Dance Room & Closet Finish Trim | FALSE | Bi-fold Primed Doors | 2000 |  |  |  | FALSE |  | FALSE
| FALSE | Primed Pre-hung 6 panel Glass Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | Primed Pre-hung 6 panel Glass Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | - Lock Sets for Doors and Closets |  |  | Home Depot | 2025-05-20 | FALSE |  | FALSE
| FALSE | Window jambs and casing |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | 7' Wire shelves for closets |  |  |  |  | FALSE |  | FALSE
| FALSE | 10' x 6' Mirror |  | 1012.93 | Waukegan Glass |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Media Area Cabinets & Fireplace | FALSE | Gas 50" Liner Fireplace Insert | 9200 | 3672.72 | Grass Roots | 2025-05-19 | TRUE | 2025-05-22 | TRUE
| FALSE | Stone Veneer from Floor to Ceiling Fireplace and Bar with Corners | 350 | 1689.04 | ProSource |  | FALSE | 2025-04-30 | FALSE
| FALSE | 2 - 36" x 96" Cabinets Glass Doors & Shelves (Material, finish, style) |  |  |  |  | FALSE |  | FALSE
| FALSE | Quartz Top for base Cabinets to match Bar In with Vanity Price |  |  | Cacjr Granite |  | FALSE | 2025-05-29 | TRUE
| FALSE | Hardware Selection (Handles) 20 + 5 |  |  | Home Depot ordered | 2025-05-19 | FALSE | 2025-05-22 | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Media & Wet Bar Plumbing | FALSE | Wet Bar Faucet & Drain | 400 |  | Ferguson | 2025-05-19 | TRUE | 2025-05-20 | TRUE
| FALSE | Wet Bar Sink |  |  |  | 2025-05-19 | TRUE | 2025-05-20 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
|  | Glass for Cabinets Media & Bar |  | 1274.8 | Waukegan Glass |  | FALSE | 2025-08-25 | FALSE
Media & Wet Bar Cabinets | FALSE | Cabinets 2- Wall with Glass; 3- Base Cabinets w/ center sink (Material, finish, style) | 4500 | 10391.7 | ProSource (all Cabinets) | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | 2 Cabinet Shelves above Sink |  |  |  |  | FALSE |  | FALSE
| FALSE | Hardware Selection (Knobs or Handles) |  |  | Home Depot |  | TRUE | 2025-05-22 | TRUE
| FALSE | Countertop Quartz Selection (edge profile) Square In with Vanity Price | 2400 | 3190 | Cacjr Granite All Quartz |  | TRUE |  | FALSE
| FALSE | Coretec Flooring - Main Area |  |  |  | 2025-04-30 | TRUE | 2025-04-30 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
Capet Add-On 4 Rooms | FALSE | 991 Sq Ft Carpet & Padding |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
|  |  | 47350 | 54253.56
|  | Allowance |  | -47350
6903.56
|  | Add-on Carpet f4 Rooms Upstairs |  | 7737.32
|  | Add-on Permit difference from Allowance 150.00 Cost 2940.00 |  | 2750.4
|  | Add-on EV charger |  | 1957
|  | Credit for 2800.00 HVAC customer paying |  | -2800
NO- Charge Installations Ceiling Fans - Cost in allowances
Note on G35: Judy Hogel: All door quote need to be confirmed with M/M Roloff
Note on G60: Judy Hogel: Wall and floor bath Tile
Note on G65: Judy Hogel: Caulk & Grout
Note on I84: Judy Hogel: All ordered together. Fans, hall light, closet, light, toilet & handle, Cabinet harware Door Stops
Note on G114: Judy Hogel: Stone total for Bar backsplash and fireplace

## Marasovich 38699-LNC Bath
|  | Allowances | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | Lead Responsible Material Recieved on Jobsite
1. Selection Phase (Choosing materials and finishes) |  |  |  |  | 2025-04-10
2025-04-14
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Base Trim for Bathroom to match exsiting |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Plumbing Fixtures | Sink 17" |  |  | Ferguson | 2025-04-14 | TRUE | 2025-04-14 | TRUE | 2025-04-15 | TRUE |  | FALSE
| Faucet |  | 139.64 | Ferguson | 2025-04-14 | TRUE | 2025-04-14 | TRUE | 2025-04-25 | TRUE |  | FALSE
| Toilet Kohler Cimarron Comfort Height Round Bowl | 400 | 280.37 | Home Depot | 2025-04-14 | TRUE | 2025-04-14 | TRUE | 2025-04-25 | TRUE |  | FALSE
| Toilet Kohler Drift Toilet Seat |  | 54.1 | Lowes | 2025-04-14 | TRUE | 2025-04-14 | TRUE | 2025-04-15 | TRUE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Electric | Device Color & Style nned 2 Toggle Switch with Double Plate |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Cabinets | Vanity - Countryside, Hallmark Door -Lily Paint + Tax | 1200 | 1032 | ProSource | 2025-04-23 | TRUE | 2025-04-25 | TRUE | 2025-04-28 | FALSE |  | FALSE
Quartz | Vanity Top Beveled Edge Carrara Morro $364.00 |  | 354 | Celso Quote sent 4/18 |  | TRUE |  | TRUE | 2025-04-28 | TRUE |  | FALSE
Vanity Handles / Knobs
Flooring | Life Proof Ivory Lane Special Order 15 day ALG HD | 337.5 | 232.38 | Home Depot | 2025-04-14 | TRUE | 2025-04-14 | TRUE | 2025-04-14 | TRUE | 2025-04-17 | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Painting | Paint Walls: Aura Bath & Spa #1394 Sugar Confite |  |  | JC Licht | Sample ordered | [5 empty] | 2025-04-17
| Paint: Ceiling Aura Bath & Spa Ceiling White |  |  | JC Licht
|  | 1937.5 | 2092.49
Note on O26: Judy Hogel: sent email deposit verfedand order 5/18
Note on C28: Judy Hogel: Note called Prodesk Mike in Algonquin 4/15 because it says out of stock. He said he would call the buyer tomorrow and see what they say.

## Belcher 38660-LNC Bath
Bath Remodeling Selection & Ordering Checklist
| Reggie Belcher 38660-LNC | Allowance | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes | PM / | Lead Jobsite
1. Selection Phase (Choosing materials and finishes)
No Permit Customer Option
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
|  |  | estimate |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Plumbing Fixtures | Sink | 1500 | 2103.68 | Ferguson |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Faucet |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Shower Head |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Shower Handle Trim |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Shower Valve |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Shower Rain Head Wall Mounted |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Shower Transfer Valve |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Hand Held Shower with Rod |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Hand held Wall Elbow |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Hand Held Vacuum Breaker |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Shower Base |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
| Shower Drain |  |  | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | TRUE |  | FALSE
[10 empty] | FALSE |  | FALSE
| Toilet Paper Holder |  |  | Home Depot |  | TRUE |  | TRUE | 2025-05-11 | TRUE |  | FALSE
| 2- Towel Bar |  | 98.22 | Home Depot |  | TRUE |  | TRUE | 2025-05-11 | TRUE |  | FALSE
| Mirror |  | 247.66 | Home Depot | 2025-05-12 | TRUE | 2025-05-12 | TRUE | 2025-05-13 | TRUE |  | FALSE
| HVAC Vent Cover |  |  | Home Depot |  | TRUE |  | TRUE | 2025-05-10 | TRUE |  | FALSE
| Shower Door | 1200 | 690.66 | Home Depot |  | TRUE |  | TRUE | 2025-05-10 | TRUE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Electric | Vanity Light | 600 |  | Ferguson |  | TRUE |  | TRUE |  | TRUE |  | FALSE
| Exhaust Fan |  |  | Ferguson |  | TRUE |  | TRUE |  | TRUE
| 2 - Light Blubs |  |  | Home Depot |  | TRUE |  | TRUE | 2025-05-11 | TRUE
| Light Switch / GFI Outlet |  |  | Home Depot |  | FALSE |  | FALSE |  | FALSE
Cabinets | Vanity | 3000 | 1276 | ProSource |  | TRUE | 2025-04-28 | TRUE | 2024-04-30 | TRUE |  | FALSE
| Handles - 7 |  |  | Home Depot |  |  | 2025-05-13 | TRUE | 2025-05-13 | TRUE
Quartz | Vanity Top |  | 935 | Cacjr Granite |  | TRUE | 2025-05-12 | TRUE | 2025-05-13 | TRUE |  | FALSE
Sentrel | Panels | 1800 | 1311 |  |  | FALSE |  | TRUE | 2025-04-30 | TRUE |  | FALSE
| Shelve/Niche |  |  |  |  | FALSE |  | TRUE | 2025-04-30 | TRUE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Flooring | LVP | 200 |  | Home depot |  | FALSE |  | TRUE | 2025-05-10 | TRUE |  | FALSE
Glass Shelves | Replace Medicine Cabinet Glass shelf |  | 125.4 | ProSource | Leadnglass Wheeling |  |  | TRUE | 2007-05-25 | FALSE |  | FALSE
| Brackets for Shelves |  | 38.94 | Home Depot
Painting | Home Deoot Replace backorder items fro Ferguson 5/19 |  | 1103.21 | [5 empty] | 2025-05-19 | FALSE |  | FALSE
|  | 8300 | 7929.77

## DeSalvo 36590-LNX Kitchen
Kitchen Remodeling Selection & Ordering Checklist
| DeSalvo, Paul and Karen 36590-LNX | Allowances | Actual Cost | Vendor | Appointment Dates |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date | Staging Location | Damaged or Returns Notes
1. Selection Phase (Choosing materials and finishes)
| *** Permit Allowance - Note: Permit not figured in CSI total | 150 | 2120 |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Plumbing | Sink | 700 | 431.92 | Home Depot |  | FALSE | 2025-04-28 | TRUE | 2025-04-30 | TRUE
| *** Confirm Drain for Garbage Disposal |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Faucet |  | 387.86 | Ferguson |  | FALSE | 2025-05-01 | TRUE | 2025-05-01 | FALSE
| *** Add-on Garbage Disposal |  | 125.39 | Amazon |  | FALSE | 2025-04-22 | TRUE | 2025-04-23 | TRUE
Electrical | Light Switches & Outlets per Code | 900 | 200 | Service Plus |  | FALSE |  | FALSE |  | FALSE
| LED under Cabinet Lighting |  | 275 | Service Plus |  | FALSE |  | FALSE |  | FALSE
| Hall Light by Garage |  | 173.19 | Lamps Plus |  | FALSE | 2025-05-08 | TRUE | 2025-05-10 | TRUE
| 8 - Recessed Lights |  | 300 | Service Plus |  | FALSE |  | FALSE |  | FALSE
| Dining Table Fixture / Fan |  | 194.88 | Lamps Plus |  | FALSE | 2025-05-06 | TRUE | 2025-05-08 | TRUE
| *Addon - Under Cabinet Bar Lights |  | 506 | Service Plus |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Cabinets | Cabinet Selection (Material, finish, style) | 24000 | 25520 | ProSource | 2025-03-14 | TRUE | 2025-03-15 | TRUE | 2025-03-19 | TRUE
| Hardware for Cabinets: Quanity |  | 155.48 | Wayfair |  | FALSE | 2025-05-27 | TRUE | 2025-05-27 | TRUE
[6 empty] | FALSE |  | FALSE |  | FALSE
Quartz | Countertop - Blanca Arabescato, Beveled Edge | 12800 | 7950 | MSI/ Celso | 2025-04-15 | TRUE | 2025-03-21 | TRUE | 2025-04-15 | TRUE
Tile | Backsplash Selection Tile | 300 | [7 empty] | FALSE
| *Tile Ragno / Look / Avio Color R8FQ |  | 582.49 | ProSource | 2025-04-15 | TRUE | 2025-04-15 | TRUE | 2025-04-16 | TRUE
| * Grout & Caulk |  | 50.53 | Floor & Décor |  | FALSE | 6.1/25 | TRUE | 2025-06-02 | TRUE
| Schulter Edging Trim for backsplash tile Matte Black |  | 27.82 | ProSource |  | FALSE | 2025-06-03 | TRUE | 2025-06-04 | TRUE
Trim | Pantry Doors, Knobs, Finish Trim & Wire Shelves | 600 |  |  |  | FALSE |  | FALSE |  | FALSE
| Double Pre-hung 6 Panel Primed door |  | 467.44 | Standard / Menards |  | FALSE | Travis | FALSE | 2025-06-02 | FALSE
| 2 1/4" Colonial Casing |  | 14.91 |  |  | FALSE | Travis | FALSE | 2025-06-02 | FALSE
| 3 1/4" Colonial Floor Base & Shoe Closet and Kitchen |  | 99.28 |  |  | FALSE | Travis | FALSE | 2025-06-02 | FALSE
| 5 - White Wire Shelves for pantry |  | 228.44 | Home Depot Travis |  | FALSE | Travis | FALSE | 2025-06-07 | FALSE
| 2 - Panty Door Knobs |  | 37.33 | Home Depot Travis |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Misc. | [5 empty] | FALSE |  | FALSE |  | FALSE
| 2- sidewall grilles-(black) |  | 151.44
| R-15 wall insulation |  | 299.35
R-38 attic insulation
| Appliances |  |  | Customer Purchased, Spec's in BT |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Total Customer Selected Items | 39300 | 38178.75
Customer Paid for Permit Credit $150.00 Change order issued 3/21/25
Customer issue credit for permit charge card fee per Jeremy
|  |  | 1121.25 | Issue Credit for unused allowance
Note on F5: Judy Hogel: paid by Customer. Credit $150.00 needed
Note on F15: Judy Hogel: Lamps plus 194.88 issued credit for $21.69 to honor sale price.
Note on J21: Judy Hogel: Final Design made sent to all for approval 3/15
Note on P21: Judy Hogel: ETA 6-8 week = 5/17
Note on M25: Judy Hogel: Sent quote to Angie 3/12 Counter table no backsplash square edging

## Carran 38348-LNX Bath
Bath Remodeling Selection & Ordering Checklist
| Janet and Jack Carran 38348-LNX | Purchased 9300.00 sales math CSI | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
[9 empty] | FALSE |  | FALSE
| Start Material Package |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Window | ProVia Kitchen Window |  | Lansing |  | TRUE |  | TRUE | 2025-02-22 | FALSE |  | FALSE
| Window Casing |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Ice & Water Shield |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Base Trim for Bathroom to match exsiting |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Travis ordered Floor and Decor Start Shower Material |  | Floor & Decor |  | FALSE |  | TRUE | 2025-01-29 | FALSE |  | FALSE
Plumbing Fixtures | Sink | 4431.67 | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Faucet |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Shower Head |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE
| Shower Handle Trim (backorder 3/24) |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Shower Valve |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Shower Transfer Trim |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Shower Transfer Valve |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Hand Held Shower with Rod |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Hand held Wall Elbow |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Hand Held Vacuum Breaker |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Shower Base |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Shower Drain |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Shower Door (Back ordered 4/14) |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21 | ferguson re order
| Toilet Paper Holder |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| 2 Hooks |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Towel Bar |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Toilet lever |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Exhaust fan |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21
| Lighted Medicine Cabinet |  | Ferguson |  | TRUE |  | TRUE | 2025-02-24 | TRUE | 2025-03-19 | FALSE | bay 21 | ferguson re order
Electric | Quad Electric Box |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Cabinets | Vanity | 1688.09 | ProSource |  | TRUE | 2025-03-01 | TRUE | 2025-03-01 | FALSE |  | FALSE
Quartz | Vanity Top | 1330 |  |  | TRUE |  | TRUE | 2025-03-09 | FALSE |  | FALSE
Tile | MSI Kaya Calactta (Wall and Floor) | 1094.28 | ProSource |  | TRUE | 2025-03-01 | TRUE | 2025-03-04 | FALSE |  | FALSE
| 6 - Schulter Edging |  | ProSource |  | TRUE | 2025-03-01 | TRUE | 2025-03-04 | FALSE |  | FALSE
| Grout (color Match Lou to order ) |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Caulk (Color match Lou to order) |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Floor & Decore | 379.93
Painting | Paint Walls: Olympic Mountains 971, Ceiling: White |  | JC Licht
Add-on | 8 - Door Knobs Replaced | 311.97 | Amazon
Black Matte Hinges - (Lou to order for Match)
9235.94

## Schemenauer 38376-LNX Kitchen
Kitchen Remodeling Selection & Ordering Checklist
|  | Peggy and Tom Schemnauer 38376-LNX | Allowances | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Damaged or Return Notes
1. Selection Phase (Choosing materials and finishes)
| TRUE | *** Permit Allowance - Add-on | 150 | 240 | Village of Gurnee |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| FALSE | Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Plumbing | TRUE | Kitchen Faucet | 700 | 430.84 | Home Depot |  | TRUE | 2025-03-09 | TRUE | 2025-03-09 | FALSE | 2025-03-26 | TRUE | Bay 25
| TRUE | Kitchen Sink |  |  | Home Depot |  | TRUE | 2025-03-09 | TRUE | 2025-03-09 | FALSE | 2025-03-26 | TRUE | Bay 25
| TRUE | *** Confirm Drain |  |  |  |  | FALSE |  | FALSE |  | FALSE | 2025-03-26 | TRUE | Bay 25 |  | (Drain attached to sink)
| FALSE | Water Line for Ice Maker |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| FALSE | Plumbing Material for Dishwasher |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Electric | FALSE | Electrical Outlets - New Location on Island | 100 | 100 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| FALSE | Replace Existing Outlets (Move Desk Outlet same Hieght) |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Cabinets | TRUE | Cabinet Selection (23) | 22000 | 25835.8 | ProSource |  | TRUE | 2025-01-25 | TRUE | 2025-01-30 | TRUE | 2025-03-19 | TRUE | Bay 25
| TRUE | Hardware for Cabinets ((15) 7 9/16” Center Pull (33) 5 1/32” Center Pull (5) Knobs. |  | 524.37 | ProSource |  | TRUE | 2025-02-10 | TRUE | 2025-02-10 |  | 2025-03-27 |  | Bay 25
[11 empty] | FALSE |  | FALSE
Counters | TRUE | Countertop Selection (Material, edge profile, color) | 8400 | 7600 | Celso |  | TRUE | 2025-02-21 | TRUE | 2025-03-09
[7 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| TRUE | Appliance Selection (Brand, model, specifications) |  |  | Customer Purchased Specs BT |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Painting | TRUE | Paint Kitchen Walls (No Ceiling paint figured) |  |  |  |  | TRUE | 2025-02-05 | FALSE |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Add-on | FALSE | Add-On Paint Ceiling |  | 1126 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
FALSE
|  |  | 31200 | 35617.01
Note on G21: Judy Hogel: $7200.00 + $400.00 for Ogee Edging

## Smrz 38462-LNC Bath
Bath Remodeling Selection & Ordering Checklist
|  | Allowance | Actual cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
[10 empty] | FALSE |  | FALSE
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Framing Material |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Drywall |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Drywall Tape |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Drywall Mud |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Shower Walls | Schulter Drain Kit Chrome |  |  | ProSource |  | FALSE |  | TRUE | 2025-02-22 | FALSE | 2025-03-26 | TRUE | Bay 21
| Schulter Shower Tray 38 x 60 | 750 | 329.62 | ProSource |  | FALSE |  | TRUE | 2025-02-22 | FALSE | 2025-03-26 | TRUE | Bay 21
| Kerdi-Board Shower Curb 48 x 6' |  |  | ProSource |  | FALSE |  | TRUE | 2025-02-22 | FALSE | 2025-03-26 | TRUE | Bay 21
| Kerdi band 5" x 16' |  |  | ProSource |  | FALSE |  | TRUE | 2025-02-22 | FALSE | 2025-03-26 | TRUE | Bay 21
| pack of 2 Kerdi - Inside corner |  |  | ProSource |  | FALSE |  | TRUE | 2025-02-22 | FALSE | 2025-03-26 | TRUE | Bay 21
| pack of 2 Kerdi - outside corner |  |  | ProSource |  | FALSE |  | TRUE | 2025-02-22 | FALSE | 2025-03-26 | TRUE | Bay 21
| Kerdi Drain Flange |  |  | ProSource |  | FALSE |  | TRUE | 2025-02-22 | FALSE | 2026-03-26 | TRUE | Bay 21
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Plumbing Fixtures | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| Moen Hand Held Shower Package |  | 437.91 | Ferguson |  | FALSE |  | FALSE |  | FALSE | 2025-03-26 | TRUE | Bay 21
| Moen Shower Handle Trim |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE | 2025-03-26 | TRUE | Bay 21
| Shower Valve | 450 |  | Ferguson |  | FALSE |  | FALSE |  | FALSE | 2025-03-26 | TRUE | Bay 21
| Moen EL Wall Supply Elbow |  |  | Ferguson |  | FALSE |  | FALSE |  | FALSE | 2025-03-26 | TRUE | Bay 21
| Toilet Wax Ring Kit (re-install SAVED Toilet) |  |  | ProSource |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Shower Door | Shower Door NOTE Order once Tile is Done |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Send Temporary Shower Rod Set-up to Customer |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
| ** ADDON Upstairs Bath Drain |  |  |  | Travis will pick up 4/23/25 | FALSE |  | FALSE | 2025-04-23 | TRUE |  | FALSE
Tile | 12 x 24 Bath Floor Tile | 650 | 1404.46 | The tile shop |  | TRUE |  | TRUE | 2025-02-11 | FALSE | 2025-03-26 | TRUE | Bay 21
| 12 x 24 Bath Wall Tile | 3200 |  | The tile shop |  | TRUE |  | TRUE | 2025-02-11 | FALSE | 2025-03-26 | TRUE | Bay 21
| Mosaic Shower Floor Tile |  |  | The tile shop |  | TRUE |  | TRUE | 2025-02-11 | FALSE | 2025-03-26 | TRUE | Bay 21
| Gold Stone Sealer |  |  | The tile shop |  | TRUE |  | TRUE | 2025-02-11 | FALSE | 2025-03-26 | TRUE | Bay 21
| 2 Package of Chrome Tile Edging |  |  | The tile shop |  | TRUE |  | TRUE | 2025-02-11 | FALSE | 2025-03-26 | TRUE | Bay 21
| Grout & Caulk (NOTE: Customer pick at start) |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Granite | Blue Pearl Granite Corner Seat, Corner Shelve and Shower Curb |  | 410 |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Shower Door | Dreamline Shower Door (To be order when Tile Done CF Size ) | 1050 |  | Ferguson - project Saved |  | FALSE |  | FALSE |  | FALSE |  | FALSE
|  | 6100 | 2581.99

## Basement Material Template
Basement Remodeling Selection, Ordering & Receiving Checklist
|  |  | Allowances | Actual Cost | Vendor | Appointment Date |  | Ordered Date |  | Received & Inspected Date | Staging Area | Damaged or Return Notes
1. Selection Phase (Choosing materials and finishes)
| FALSE | *** Permit Allowance - Add-on | 150 |  |  |  | FALSE |  | FALSE
Electrical - Reccessed all | FALSE | 33 - LED recessed lights (18 for open area, 6 for dance room, 9 for media room) | 3700 |  |  |  | FALSE |  | FALSE
Electrical - Bath | FALSE | Bath Exhusted Fan |  |  |  |  | FALSE |  | FALSE
Electrical - Bath | FALSE | Bath Vanity Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bath | FALSE | Recessed Shower Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bath | FALSE | 4 Bath Switches |  |  |  |  | FALSE |  | FALSE
Electrical - Dance | FALSE | Dance Room 6 Recessed Lights |  |  |  |  | FALSE |  | FALSE
Electrical - Dance | FALSE | Dance Room closet Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bedroom | FALSE | Bedroom Fixture |  |  |  |  | FALSE |  | FALSE
Electrical - Bedroom | FALSE | Bedroom Closet Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bedroom | FALSE | 3 Light Switches |  |  |  |  | FALSE |  | FALSE
Electrical - Media | FALSE | Cabinet Lighting (next to fireplace) |  |  |  |  | FALSE |  | FALSE
Electrical - Wet Bar | FALSE | Cabinet Lighting under and inside wall cabinets |  |  |  |  | FALSE |  | FALSE
| FALSE | Electric Outlets for all areas |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Flooring - Open Area | FALSE | Luxury Vinyl Plank (LVP) flooring – 1,000 sq. ft. | 5000 |  |  |  | FALSE |  | FALSE
Flooring - Bedroom & Closet | FALSE | Carpet and padding (for bedroom and closet) | 2500 |  |  |  | FALSE |  | FALSE
Flooring - Dance Room & Closet | FALSE | Pre-finished oak flooring (for dance room and closet) | 1400 |  |  |  | FALSE |  | FALSE
Flooring - Bathroom | FALSE | Radiant Heat Mat | 700 |  |  |  | FALSE |  | FALSE
| FALSE | Bath Floor Tile |  |  |  |  | FALSE |  | FALSE
| FALSE | Grout to match |  |  |  |  | FALSE |  | FALSE
| FALSE | Caulk to match |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Painting - Open Area | FALSE | Spray Ceiling to unfinished ceiling framing, mechanicals & HVAC | Included |  |  |  | FALSE |  | FALSE
Painting - Dance Room | FALSE | Spray Ceiling to unfinished ceiling framing, mechanicals & HVAC | Included |  |  |  | FALSE |  | FALSE
Painting - Bathroom | FALSE | Paint Ceiling, Walls, Door & Trim | Included |  |  |  | FALSE |  | FALSE
Painting - Bedroom | FALSE | Paint Ceiling, Walls, Closet, Doors, & Trim | Included |  |  |  | FALSE |  | FALSE
Painting - Media Room | FALSE | Paint Ceiling, Wall, Floor Base, Shoe Mold, Door Jamb and Casing | Included |  |  |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Finish Trim - Open, Media, 3 Closets | FALSE | Pre-hung Primed 6-panel doors: Unders Stairs, Walk-in, Furnace & Sump Pump |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | (4) - Lock Sets for Doors and Closets |  |  |  |  | FALSE |  | FALSE
| FALSE | Window jambs and casing |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | 30' Wire shelves for closets |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Bathroom Plumbing | FALSE | Shower Valve |  |  |  |  | FALSE |  | FALSE
| FALSE | Shower Head |  |  |  |  | FALSE |  | FALSE
| FALSE | Schulter Shower Drain Kit |  |  |  |  | FALSE |  | FALSE
| FALSE | Toilet |  |  |  |  | FALSE |  | FALSE
| FALSE | Water valve, wax ring, and water line |  |  |  |  | FALSE |  | FALSE
| FALSE | Sink (Note: Not in contract) |  |  |  |  | FALSE |  | FALSE
| FALSE | Quartz Top |  |  |  |  | FALSE |  | FALSE
| FALSE | Faucet & Drain Kit |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Shower & Bath Tile | FALSE | Schulter Shower Base 48" x 36" |  |  |  |  | FALSE |  | FALSE
| FALSE | Shower Base Tile 12 Sq Ft |  |  |  |  | FALSE |  | FALSE
| FALSE | Shower Wall Tile 92 Sq Ft |  |  |  |  | FALSE |  | FALSE
| FALSE | Quartz caps for shower curb, seat 12" x 18" , and niche |  |  |  |  | FALSE |  | FALSE
| FALSE | Grout to match all |  |  |  |  | FALSE |  | FALSE
| FALSE | Caulk to match all |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Bathroom Finish Trim | FALSE | Pre-hung Primed 6-panel door |  |  |  |  | FALSE |  | FALSE
| FALSE | Primed 6 panel Pocket Door Slab |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | (1) - Lock Sets for Door |  |  |  |  | FALSE |  | FALSE
| FALSE | Pocket Door Hardware |  |  |  |  | FALSE |  | FALSE
| FALSE | 36" Vanity Cabinet |  |  |  |  | FALSE |  | FALSE
| FALSE | Quartz Top |  |  |  |  | FALSE |  | FALSE
| FALSE | Hanging mirror |  |  |  |  | FALSE |  | FALSE
| FALSE | 2 - Towel bars or Hooks |  |  |  |  | FALSE |  | FALSE
| FALSE | T.P. Holder |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Bath Shower Encloser | FALSE | Glass shower door enclosure (60”x76”) |  |  |  |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Bedroom & Closet Finish Trim | FALSE | Window Jams 3 1/2' Primed Colonial Casing |  |  |  |  | FALSE |  | FALSE
| FALSE | 2 - Pre-hung Primed 6-panel door |  |  |  |  | FALSE |  | FALSE
| FALSE | Primed 6 panel Pocket Door Slab |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | (2) - Lock Sets for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 16 LN FT of Wire White Shelving |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Dance Room & Closet Finish Trim | FALSE | Bi-fold Primed Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | Primed Pre-hung 6 panel Glass Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | Primed Pre-hung 6 panel Glass Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | - Lock Sets for Doors and Closets |  |  |  |  | FALSE |  | FALSE
| FALSE | Window jambs and casing |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | 7' Wire shelves for closets |  |  |  |  | FALSE |  | FALSE
| FALSE | 10' x 6' Mirror |  |  |  |  | FALSE |  | FALSE
| FALSE |  |  |  | ☐ Cabinet moldings and hardware |  | FALSE |  | FALSE
Media Area Cabinets & Fireplace | FALSE | Gas 46" Liner Fireplace Insert |  |  | ☐ Quartz countertop and undermount sink |  | FALSE |  | FALSE
| FALSE | Stone Veneer from Floor to Ceiling |  |  |  |  | FALSE |  | FALSE
| FALSE | 2 - 36" x 96" Cabinets Glass Doors & Shelves (Material, finish, style) |  |  | ☐ Wet bar faucet, sink, and drain kit |  | FALSE |  | FALSE
| FALSE | Cabinet Furniture Base and Crown |  |  |  |  | FALSE |  | FALSE
| FALSE | Hardware Selection (Knobs or Handles) |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Media & Wet Bar Plumbing | FALSE | Wet Bar Faucet & Drain |  |  |  |  | FALSE |  | FALSE
| FALSE | Wet Bar Sink |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Media & Wet Bar | FALSE | Cabinets 2- Wall with Glass; 3- Base Cabinets w/ center sink (Material, finish, style) |  |  |  |  | FALSE |  | FALSE
| FALSE | 2 Cabinet made Shelves above Sink |  |  |  |  | FALSE |  | FALSE
| FALSE | Hardware Selection (Knobs or Handles) |  |  |  |  | FALSE |  | FALSE
| FALSE | Countertop Quartz Selection (edge profile) |  |  |  |  | FALSE |  | FALSE
| FALSE | Stone Veneer Backsplash |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
|  |  | 13300 | 0

## Bath Template
Bath Remodeling Selection & Ordering Checklist
|  | Allowance | Actual Cost | Vendor | Appointment Date |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
| Start Material Package |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Plumbing Fixtures | Sink |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Faucet |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Head |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Handle Trim (backorder 3/24) |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Valve |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Transfer Trim |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Transfer Valve |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Hand Held Shower with Rod |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Hand held Wall Elbow |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Hand Held Vacuum Breaker |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Base |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Drain |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Shower Door (Back ordered 4/14) |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Toilet Paper Holder |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| 2 Hooks |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Towel Bar |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Toilet lever |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Exhaust fan |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
| Lighted Medicine Cabinet |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Electric | Quad Electric Box |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Cabinets | Vanity |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Quartz | Vanity Top |  |  |  |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Tile | [5 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE |  | FALSE
Painting
Add-on

## Kitchen Template
Kitchen Remodeling Selection & Ordering Checklist
|  | Allowances | Actual Cost | Vendor | Appointment Dates |  | Selection Complete Date |  | Ordered Date |  | Received & Inspected Date | Staging Area | Damaged or Return Notes
1. Selection Phase (Choosing materials and finishes)
| *** Permit Allowance - Note: Permit not figured in CSI total |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Start Material |  |  |  |  | FALSE |  | FALSE |  | FALSE
Plumbing | Refrigerator Water Line |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Water Valve Box |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Sink |  |  |  |  | FALSE |  | FALSE |  | FALSE
| *** Confirm Drain |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Fauet |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Electrical | Light Switches & Outlets per Code |  |  |  |  | FALSE |  | FALSE |  | FALSE
| LED under Cabinet Lighting |  |  |  |  | FALSE |  | FALSE |  | FALSE
| 4 - Pendant Fixtures |  |  |  |  | FALSE |  | FALSE |  | FALSE
| 8 - Recessed Lights |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Dining Table Fixture |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Pantry Light |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Cabinets | Cabinet Selection (Material, finish, style) |  |  |  |  | FALSE |  | FALSE |  | TRUE
| Hardware for Cabinets: Quanity |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Quartz | Countertop Selection (Material, edge profile, color) |  |  |  |  | FALSE |  | FALSE |  | FALSE
Tile | Backsplash Selection Tile |  |  |  |  | FALSE |  | FALSE |  | FALSE
| * Grout |  |  |  |  | FALSE |  | FALSE |  | FALSE
| * Caulk |  |  |  |  | FALSE |  | FALSE |  | FALSE
| * Edging |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
Trim | Pantry Doors, Knobs, Finish Trim & Wire Shelves |  |  |  |  | FALSE |  | FALSE |  | FALSE
| Double Pre-hung 6 Panel Primed door |  |  |  |  | FALSE |  | FALSE |  | FALSE
| 2 1/4" Colonial Casing |  |  |  |  | FALSE |  | FALSE |  | FALSE
| 3 1/4" Colonial Floor Base & Shoe Closet and Kitchen |  |  |  |  | FALSE |  | FALSE |  | FALSE
| 5 - White Wire Shelves for pantry |  |  |  |  | FALSE |  | FALSE |  | FALSE
| 2 - Panty Door Knobs |  |  |  |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Appliances |  |  | Customer Purchased, Spec's in BT |  | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
[6 empty] | FALSE |  | FALSE |  | FALSE
| Total Customer Selected Items | 0 | 0