## Vance, Stacey & Terry 39505-LNC
Bath Remodel
| Terry & Stacey Vance | Model | Allowance | Actual Cost | Vendor | Ordered Date |  | Received & Inspected Date |  | Staging Location | Return or Damaged Notes
1. Selection Phase (Choosing materials and finishes)
Powder Room | [6 empty] | FALSE |  | FALSE
| Vanity 21 x 30 Hanover / Carbon |  | 3200 | 3100 | Shiloh Order | 2025-11-21 | TRUE |  | FALSE
| Hardware Handles | K-26640-2MB |  | 61.138 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Quartz Top Back & Side Splash SQUARE | Calacatta Botanica |  |  | CACJR Granite Quote REQ 11/22 |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
| Sink | K-2209-0 | 300 | 99.198 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Faucet & Drain | K-22022-4-2MB | 350 | 357.962 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Toilet | K-30810-0 | 300 | 416.9 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Toilet Paper Holder | K-21954-2MB |  | 68.013 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Towel Ring | K-21955-2MB |  | 50.996 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Mirror | K-26050-BLG | 400 | 227.931 | Ferguson | 2025-11-21 | TRUE |  | FALSE
| Vanity Light | K-31757-S03-2GL | 350 | 364.518 | Ferguson | 2025-11-21 | TRUE |  | FALSE
[7 empty] | FALSE |  | FALSE
Paint | Paint 2 Colors Twilight 2058-10 & Garytint 1611 |  |  |  | Benjamin Moore | 2025-11-22 | TRUE |  | FALSE
| Ceiling White | [5 empty] | FALSE |  | FALSE
| Trim | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Doors & BaseBoard | [6 empty] | FALSE |  | FALSE
| 4 Doors - 2 Panel Solid |  | 2100 |  |  |  | FALSE |  | FALSE
| 3- Door Knobs 2 passage 1 privacy | [5 empty] | FALSE |  | FALSE
| 1 Bi-Fold Knobs Matte Black |  |  | 12.35 | Wayfair | 2025-11-22 | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
| Total Allowances to Actual Costs |  | 7000 | 4759.006 |  |  | FALSE |  | FALSE
| Allowance | [5 empty] | FALSE |  | FALSE
| Over Allowance Materials Add-On |  |  | 4759.006 |  |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
| Total Allowances |  | 14000