## Roloff 38562-LNC Basement
Basement Remodeling Selection, Ordering & Receiving Checklist
Christine Roloff 38563-LNC |  | bath floor & shower walls) | Allowances | Actual Cost | Vendor | Appointment Date |  | Ordered Date |  | Received & Inspected Date
1. Selection Phase (Choosing materials and finishes)
| FALSE | *** Permit Allowance - | 150 | 2900.4 |  |  | FALSE |  | TRUE
Electrical - Reccessed all | FALSE | 33 - LED recessed lights (18 for open area, 6 for dance room, 9 for media room) | 3700 | 1414 |  |  | FALSE |  | TRUE
Electrical - Bath | FALSE | Bath Exhusted Fan |  |  | Amazon |  | FALSE | 2025-05-03 | TRUE
Electrical - Bath | FALSE | Bath Vanity Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bath | FALSE | Recessed Shower Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bath | FALSE | 4 Bath Switches |  |  |  |  | FALSE |  | FALSE
Electrical - Dance | FALSE | Dance Room 6 Recessed Lights |  |  |  |  | FALSE |  | FALSE
Electrical - Dance | FALSE | Dance Room closet Light |  |  |  |  | FALSE |  | FALSE
Electrical - Bedroom | FALSE | Bedroom Fan 42" |  |  | Home Depot | 2025-05-20 | TRUE | 2025-05-22 | TRUE
Electrical - Bedroom | FALSE | Bedroom Closet Light - Motion Sensored |  |  | Home Depot |  | FALSE |  | FALSE
Electrical - Bedroom | FALSE | 3 Light Switches |  |  |  |  | FALSE |  | FALSE
Electrical - Media | FALSE | Cabinet Lighting (next to fireplace) |  |  |  |  | FALSE |  | FALSE
Electrical - Wet Bar | FALSE | Cabinet Lighting under and inside wall cabinets |  |  |  |  | FALSE |  | FALSE
| FALSE | Electric Outlets for all areas |  |  |  |  | FALSE |  | FALSE
| FALSE | ** 50" Fan Media Room |  |  | Home Depot | 2025-05-20 | TRUE | 2025-05-22 | TRUE
Flooring - Open Area | FALSE | Coretec Luxury Vinyl Plank (LVP) flooring – 1,000 sq. ft. | 5000 | 7039.26 |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | 3 Coretec Carpert Reducers |  |  |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | 2 Coretec T-Molding |  |  |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
Flooring - Bedroom & Closet | FALSE | Carpet and padding (for bedroom and closet) 280 SQ Ft | 2500 | 1024.21 |  | 2025-04-29 | TRUE | 2025-04-30 | FALSE
Flooring - Dance Room & Closet | FALSE | Pre-finished oak flooring (for dance room and closet) | 1400 | 4970 | Material 3616.20 Mr Floor |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Painting - Open Area Ceiling | FALSE | Spray Ceiling to unfinished ceiling framing, mechanicals & HVAC | Included |  |  |  | FALSE |  | FALSE
Painting - Dance Room | FALSE | Spray Ceiling to unfinished ceiling framing, mechanicals & HVAC | Included |  |  |  | FALSE |  | FALSE
Painting - Bathroom | FALSE | Paint Ceiling, Walls, Door & Trim | Included |  |  |  | FALSE |  | FALSE
Painting - Bedroom | FALSE | Paint Ceiling, Walls, Closet, Doors, & Trim | Included |  |  |  | FALSE |  | FALSE
Painting - Media Room | FALSE | Paint Ceiling, Wall, Floor Base, Shoe Mold, Door Jamb and Casing | Included |  |  |  | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Finish Trim - Open, Media, 3 Closets | FALSE | Pre-hung Primed 6-panel doors: Unders Stairs, Walk-in, Furnace & Sump Pump | 2800 | 4500.65 |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | (4) - Lock Sets for Doors and Closets |  | 400.28 |  |  | FALSE |  | FALSE
| FALSE | Window jambs and casing |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  | 2750 |  |  | FALSE |  | FALSE
| FALSE | 30' Wire shelves for closets (Lou to order) |  | 429.99 | Home depot aLL CLOSETS |  | FALSE | 2025-08-25 | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Bathroom Plumbing | FALSE | Shower Valve | 2300 | 2423.39 | Ferguson | 2025-04-29 | TRUE | 2025-05-21 | TRUE
| FALSE | Shower Head |  |  |  |  | FALSE | 2025-05-21 | TRUE
| FALSE | Schulter Shower Drain Kit |  |  |  |  | FALSE | 2025-06-05 | TRUE
| FALSE | Toilet |  | 1181.64 | Home Depot (fans, Toiliet ) Handles Door Stops |  | FALSE | 2025-05-22 | TRUE
| FALSE | Toilet Kohler Flush handle Matte Black |  |  | Home Depot |  | FALSE | 2025-05-22 | TRUE
| FALSE | Water valve, wax ring, and water line |  |  |  |  | FALSE |  | FALSE
| FALSE | Sink (Note: Not in contract) |  |  | Ferguson |  | FALSE | 2025-05-21 | TRUE
| FALSE | Quartz Top |  |  | Crajr Granite | 2025-04-30 | FALSE | 2025-05-29 | TRUE
| FALSE | Faucet & Drain Kit |  |  | Ferguson |  | FALSE | 2025-05-21 | TRUE
| FALSE | Exhaust Fan with Light |  | 179.68 | Amazon |  | FALSE | 2025-05-03 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Shower & Bath Tile | FALSE | Schulter Kerdi Shower Tray 36 x 48 | Included |  | ProSource |  | TRUE | 2025-04-30 | TRUE
Shower & Bath Tile | FALSE | Schulter Shower Curb 48" x 36" | Included |  | ProSource |  | TRUE | 2025-04-30 | TRUE
Shower & Bath Tile | FALSE | Schulter Kerdi Right & Left Corners | Included |  | ProSource |  | TRUE | 2025-04-30 | TRUE
Flooring - Bathroom | FALSE | Radiant Heat Mat (lou to order) |  | 736.23 | Warmly Yours |  | FALSE | 2025-07-16 | TRUE
| FALSE | Shower Base Tile 15 Sq Ft | 2500 | 1486.96 | ProSource | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | Shower Wall Tile 120 Sq Ft (ordered 171.6 SQ FT for Bath floor& shower walls) |  |  |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | Bath Floor Tile 50 Sq Ft | 700 |  |  | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | Schulter Edging 32 Linear Ft = 5 pieces |  |  | ProSource w/tile |  | FALSE | 2025-04-30 | TRUE
| FALSE | Quartz caps for shower curb, seat 12" x 18" , and niche All QUARTZ |  |  | Cacjr Quartz |  | FALSE | 2025-05-20 | TRUE
| FALSE | 50 LBS - Grout to match all Smoke Grey - 89 (2 bags) |  | 101.07 | Floor & Décor | 2025-04-29 | TRUE | 2025-05-22 | TRUE
| FALSE | 2 - Caulk to match all Smoke Grey - 89 |  |  | Floor & Décor | 2025-04-29 | FALSE | 2025-05-22 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
Bathroom Finish Trim | FALSE | Pre-hung Primed 6-panel door | 3000 |  |  |  | FALSE |  | FALSE
| FALSE | Primed 6 panel Pocket Door Slab |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | (1) - Lock Sets for Door |  | 31.9 | Home Depot | 2025-05-22 | FALSE | 2025-08-26 | FALSE
| FALSE | Pocket Door Hardware |  |  |  |  | FALSE |  | FALSE
| FALSE | 2 Bi-Pass Cups Matte Black |  |  | Home Depot | 2025-05-22 | FALSE |  | FALSE
| FALSE | 36" Vanity Cabinet |  | cabinet order | ProSource | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | Quartz Top |  |  | Cacjr Quartz |  | FALSE | 2025-05-30 | TRUE
| FALSE | Hanging mirror |  | 85.51 | Amazon |  | FALSE | 2025-05-19 | TRUE
| FALSE | Kohler Numista 3 piece Bath set |  | 133.52 | Home Depot | 2025-04-29 | TRUE | 2025-05-02 | TRUE | 2025-05-19 | Noted Judy Picked up
| FALSE | Kohler Numista Robe Hook |  |  | Home Depot | 2025-04-29 | TRUE | 2025-05-02 | TRUE | 2025-05-19 | Left on office
| FALSE | Kohler Numista 18" Towel Bar |  |  | Home Depot | 2025-04-29 | TRUE | 2025-05-02 | TRUE | 2025-05-19 | Counter
| FALSE | Bath Vanity Liight |  | 121 | Littman Bros |  | FALSE | 2025-06-06 | FALSE
| FALSE | Lights, toilet, toilet handle, cabinet handles, Door stops |  | 719.02 | Home Depot |  | FALSE | 2025-05-22 | TRUE
| FALSE | 14 Spring Door Stops - white |  |  | Home Depot |  | FALSE | 2025-05-22 | TRUE
| FALSE | 10 - Hinges Door Stops - White |  |  | Home Depot |  | FALSE | 2025-05-22 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Bath Shower Encloser | FALSE | Glass shower door enclosure (60”x76”) | 3400 | 3294.06 | Waukegan Gurnee Glass Company |  | FALSE |  | TRUE
[7 empty] | FALSE |  | FALSE
Bedroom & Closet Finish Trim | FALSE | Window Jams 3 1/2' Primed Colonial Casing | 1200 |  |  |  | FALSE |  | FALSE
| FALSE | 2 - Pre-hung Primed 6-panel door |  |  |  |  | FALSE |  | FALSE
| FALSE | Primed 6 panel Pocket Door Slab |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | (2) - Lock Sets for Doors |  |  | Home Depot | 2025-05-20 | TRUE |  | FALSE
| FALSE | 16 LN FT of Wire White Shelving |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Dance Room & Closet Finish Trim | FALSE | Bi-fold Primed Doors | 2000 |  |  |  | FALSE |  | FALSE
| FALSE | Primed Pre-hung 6 panel Glass Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | Primed Pre-hung 6 panel Glass Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | 3 1/2" Colonial Casing for Doors |  |  |  |  | FALSE |  | FALSE
| FALSE | - Lock Sets for Doors and Closets |  |  | Home Depot | 2025-05-20 | FALSE |  | FALSE
| FALSE | Window jambs and casing |  |  |  |  | FALSE |  | FALSE
| FALSE | 4 1/4" Colonial floor base and shoe molding |  |  |  |  | FALSE |  | FALSE
| FALSE | 7' Wire shelves for closets |  |  |  |  | FALSE |  | FALSE
| FALSE | 10' x 6' Mirror |  | 1012.93 | Waukegan Glass |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
Media Area Cabinets & Fireplace | FALSE | Gas 50" Liner Fireplace Insert | 9200 | 3672.72 | Grass Roots | 2025-05-19 | TRUE | 2025-05-22 | TRUE
| FALSE | Stone Veneer from Floor to Ceiling Fireplace and Bar with Corners | 350 | 1689.04 | ProSource |  | FALSE | 2025-04-30 | FALSE
| FALSE | 2 - 36" x 96" Cabinets Glass Doors & Shelves (Material, finish, style) |  |  |  |  | FALSE |  | FALSE
| FALSE | Quartz Top for base Cabinets to match Bar In with Vanity Price |  |  | Cacjr Granite |  | FALSE | 2025-05-29 | TRUE
| FALSE | Hardware Selection (Handles) 20 + 5 |  |  | Home Depot ordered | 2025-05-19 | FALSE | 2025-05-22 | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
[7 empty] | FALSE |  | FALSE
Media & Wet Bar Plumbing | FALSE | Wet Bar Faucet & Drain | 400 |  | Ferguson | 2025-05-19 | TRUE | 2025-05-20 | TRUE
| FALSE | Wet Bar Sink |  |  |  | 2025-05-19 | TRUE | 2025-05-20 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
|  | Glass for Cabinets Media & Bar |  | 1274.8 | Waukegan Glass |  | FALSE | 2025-08-25 | FALSE
Media & Wet Bar Cabinets | FALSE | Cabinets 2- Wall with Glass; 3- Base Cabinets w/ center sink (Material, finish, style) | 4500 | 10391.7 | ProSource (all Cabinets) | 2025-04-29 | TRUE | 2025-04-30 | TRUE
| FALSE | 2 Cabinet Shelves above Sink |  |  |  |  | FALSE |  | FALSE
| FALSE | Hardware Selection (Knobs or Handles) |  |  | Home Depot |  | TRUE | 2025-05-22 | TRUE
| FALSE | Countertop Quartz Selection (edge profile) Square In with Vanity Price | 2400 | 3190 | Cacjr Granite All Quartz |  | TRUE |  | FALSE
| FALSE | Coretec Flooring - Main Area |  |  |  | 2025-04-30 | TRUE | 2025-04-30 | TRUE
| FALSE | [5 empty] | FALSE |  | FALSE
Capet Add-On 4 Rooms | FALSE | 991 Sq Ft Carpet & Padding |  |  |  |  | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
| FALSE | [5 empty] | FALSE |  | FALSE
|  |  | 47350 | 54253.56
|  | Allowance |  | -47350
6903.56
|  | Add-on Carpet f4 Rooms Upstairs |  | 7737.32
|  | Add-on Permit difference from Allowance 150.00 Cost 2940.00 |  | 2750.4
|  | Add-on EV charger |  | 1957
|  | Credit for 2800.00 HVAC customer paying |  | -2800
NO- Charge Installations Ceiling Fans - Cost in allowances
Note on G35: Judy Hogel: All door quote need to be confirmed with M/M Roloff
Note on G60: Judy Hogel: Wall and floor bath Tile
Note on G65: Judy Hogel: Caulk & Grout
Note on I84: Judy Hogel: All ordered together. Fans, hall light, closet, light, toilet & handle, Cabinet harware Door Stops
Note on G114: Judy Hogel: Stone total for Bar backsplash and fireplace